## Sheet1
EKITI STATE ACTION ON BUSINESS ENABLING REFORMS (SABER)
2025 BERAP PROGRESS REPORT
Progress update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date | Status | Explanation of Action not Completed | Next Steps | PEBEC Comments
1 | Improved transparency in Land Administration and Land-based Investment Process | (i) This reform area will enhance the administration and management of land in Ekiti State; (ii) the reform will also improve transparency in property registration and unlock capital from this asset class. | A.1.Establish and build consensus among relevant MDAs on institutional and policy reforms being proposed and/or implemented including but not limited to developing and maintaining digital titling of all landed properties in Ekiti | 1. Ensure at least 80% of buildings in major towns (Ado, Ikere and Ikole LGAs) are enumerated and recorde by December 31, 2025 2. Ensure 100% of new CofOs are digitzed and archived by December 31, 2025. | Land Administration and Management Project (LAMP) Committee, GIS - Bureau of Land Services, Director of Deed Registry, Bureau of Land Services (for CofO), Director Physical Planning & Development Matters - Ministry of Physical Planning and Urban Development (for Construction Permits), Cordinator, Ekiti State Geospatial Centre - Bureau of Land Services (for digitization of existing CofOs) | Office of the Governor, Office of the Secretary to the State Government, Ministry of Finance and Economic Development, Ministry of Justice , Bureau of Land Services, Ministry of Physical Planning & Urban Development, Ekiti State Internal Revenue Service, Ekiti State Development and Investment Promotion Agency (EKDIPA), Ministry of Agriculture and Food Security, Bureau of Information, Communication and Technology | N125,000,000 | 2025-01-01 | 2025-12-31 | Completed
|  |  | A.2. Publish the updated process for obtaining a certificate of occupancy (CofO) including all relevant MDAs, timelines and cost on the state's official website and EKDIPA's website | [6 empty] | Completed
|  |  | A.3. Publish the updated process for obtaining construction permit including all relevant MDAs, timelines and cost on the State official website | [6 empty] | Completed
|  |  | A.4. carryout the digitization and indexation on all the new CofOs registered in the year 2025 | [6 empty] | Delayed | It was delayed because: (i) The inclusion of the Applicant Legal Identification (ID) field as a search parameter in the Digital Archiving System (DAS) was inadvertently omitted during the system configuration process. (ii) In addition, the document was not generated in the prescribed PDF/A archival format. Both issues have been identified and the process is currently under review for necessary corrective action. | 1. System enhancement, Integration of NIN/ Government ID field, Functional testing, User acceptance testing and depolyment (Completed) 2. Progressive digitization and PDF/A conversion of legacy records (May - December 2026) 3. Batch migration of converted records into Digital Archiving System ( DAS) (July- December2026)
|  |  | B.1. Sustain the implemementation of the FRILIA Toolkit/Guildelines | 1. Quarterly Implementation Report on FRILIA in Ekiti State 2. At least 3 sessions of train-the-trainers programmes | Director Agric Services, Ministry of Agriculture and Food Security | Bureau of Land Services, Office of Surveyor-General, Ministry of Finance, Agriculture Development Project, Farm Settlement, Ministry of Industry, Trade & Investment,Ekiti State Development and Investment Promotion Agency (EKDIPA), Ekiti State Internal Revenue Service, Ministry of Justice, State House of Assembly |  |  |  | Delayed | The State has operationalized the Investment Approval Process (IAP) and the eight (8) FRILIA Toolkits as standard reference frameworks for relevant MDAs involved in the implementation and regulation of large-scale agricultural investments. To support institutionalization and stakeholder buy-in, a FRILIA Stakeholders' Engagement Workshop has been conducted successfully. Building on this achievement, a minimum of two additional Train-the-Trainers and stakeholder engagement programmes will be organized during the third and fourth quarters of 2026 to further strengthen capacity, promote compliance, and ensure the sustained implementation of FRILIA principles within the State. There was delay because; i. Lenghty negotiation process due to investor's demand for clear risk-sharing mechanisms and guarantee ii. Etended stakeholders consultation timeline due to the need for Free, Prior and Informed Consent (FPIC) processes. iii. Insufficient baseline data on soil quality and socio-economic | 1. Engagement of the three prospective investors for the implementation of FRILIA-compliant projects in Soybean, Cassava, and Maize value chains. (Completed) 2. Undertake project preparation activities, including site identification, stakeholder consultations, baseline assessments, with the application of the FRILIA Toolkits and Investment Approval Process (IAP). (June - December2026) 3. Execute Memoranda of Understanding (MoUs) and other necessary agreements with the selected investors to formalize the pilot schemes. (July 2026) 4. Commence implementation of the pilot FRILIA projects for Soybean, Cassava, and Maize across the three Agro-Ecological Zones. 9July - December 2026) 5. Monitor and document the implementation of the pilot schemes to assess compliance with FRILIA principles and measure socio-economic and environmental impacts. (January - December 2026) 6. Evaluate lessons learned and develop a scale-up framework for replicating successful FRILIA-compliant investments across the State. ( October 2026 - January 2027)
|  |  | B.2. prodcution of Report on the implementation of FRILIA on qaurterly basis for the considetaion of the State Steering Committee | [6 empty] | Completed
|  |  | B.2. Offer ongoing training for government officials and other stakeholders on FRILIA, land governance best practices, transparency, and ethical conduct. | [6 empty] | Completed
2 | Improved infrastructure for enhancement of business-enabling environment (regulatory framework for private investment in fibre optic infrastructure) | To build a conducive legal, regulatory and institutional framework for a thriving digital economy. | A.1. Maintenace of the aggregate per linear meter fees for broadband deployment | 1. Ensure a law that caps the Right of Way tariff at not more than N145 per linear meter is enacted. 2. Ensure deployment of GPON fibre infrastructure across Ekiti State in at least 2,000km across the State. 3. Increase of more that 80% in the total deployed GPON fibre optic cable kilometers against 2022 as baseline. | Director of Planning Permit, Ministry of Physical Planning and Urban Development, Director of Information and Communication Technology, Ministry of Innovation, Science & Digital Economy | Ministry of Physical Planning and Urban Development, Office of the surveyor General, Ministry of Public Infrastructure and Public Utility , Ministry of Finance & Economic Development, Ekiti State Development and Investment Promotion Agency (EKDIPA), Bureau of Information and Communication Technology, Ministry of Physical Planning and Urban Development, Ekiti State Internal Revenue Service,, Ministry of Justice, State House of Assembly | Not ApplicableF12:H18L18G12:H22E12:H18 | 2025-01-01 | 2025-12-31 | Delayed | Processing the regulation into law is on-going Specify the reason for the delay in completion. i.The ratification of the document is subject to the State Executive Council meeting which is yet to be convened (Tentatively scheduled for July 2026). ii. Immediately the bill is approved by the EXCO, it will be forwarded to the State House of Assembly for passage imto Law ( Tentatively scheduled for July 2026) iii. Publication of the Right of Way Tarrif Law ( Q4 2026) | Realisation of the successful processing of the optic fibre regulation into a law that caps the right of way tariff is achieved in 2026
|  |  | B. Publication of Right of Way (ROW) related requests by operators during the year 2025 | [6 empty] | Completed | One applicaton was received and published before the end of the year 2025. | Organize and conduct quarterly engagement meetings with operators to facilitate continuous dialogue and feedback. ( July - Sept 2026)
|  |  | B.1 Publication of updated framework for the ROW process in the State | [6 empty] | Completed |  | Keep updating as changes occurs
|  |  | B.2. Engage qualified service providers for the deployment of non-Gigabit Passive Optical Network (GPON) fibre optic cable kilometres | [6 empty] | Completed
|  |  | C.1 Increase in total deployed GPON fibre optic cable kilometres against 2022 baseline meets target. | [6 empty] | Delayed | Implementation was delayed as the service providers contacted to extend optic fibre coverage did not proceed with the proposed deployment within the planned timeframe. | More engagement in the following year with consultant in each quarter of the year. (Q1-Q4) Meetings were held with JUS Parther Limited representing Airtel and Global Independent Connect Limited (GICL) in March 2026. The two (2) Companies have been approved. for immediate implementation
|  |  | C.2. Engage with private sector investors and telecom operators to gather feedback on regulatory challenges and opportunities, using it to guide ongoing policy reforms | [6 empty] | Completed
|  |  | C.3. Establish a single, centralized platform for processing RoW requests, tracking their status, and addressing delays or disputes | [6 empty] | Delayed | Implementation process with Bureau of Information, Communication & Technology (BICT) is on going. The process was delayed because; i. The setting up of a single centralised platform for processing ROW requests, tracking their status as well as addresing the delay involved a series of engagements and discussions before the Ministry of Urban Development and Bureau of ICT could come up with a reasonable template in line with the reform action plan , | i. Continue engagement and discussion with BICT for actualizing the reform action in the following year (QI-Q4). ii. The expected delivery date of the system is September 2026. Please note that templates for application system, demand notice and tracking have been provided for the Bureau of ICT.
3 | Sustainable Large-Scale Investments | to establish effective Public-Private Partnership (PPP) models in the State | A.Establish key performance indicators (KPIs) to track the success of investment projects, ensuring they meet economic, environmental, and social objectives | 1. Develop comprehensive KPI for purpose of mornitoring and evalution 2. Establish a State Wealth Fund which will include Project Facilitation Fund to catalyze private investments | Director of Investment, Ekiti State Development and Investment Promotion Agency (EKDIPA); Director of State Finances, Ministry of Finance and Economic Development | E | 20500000 | 2025-01-01 | 2025-12-31 | Completed
|  |  | A.1 Ensure that the PPP unit is staffed with experts in finance, law, project management, and sector-specific areas (e.g., infrastructure, health, education) to ensure it can effectively manage complex projects | [6 empty] | Completed
|  |  | A.2Train government officials, particularly those in the PPP unit, on project management, contract negotiation, risk analysis, and financial modeling to effectively manage PPP projects | [6 empty] | Completed
|  |  | B. Establishment of State Project Facilitation Fund with a minimum funding of 3% of the total pipeline estimated capital investment | [6 empty] | Delayed | The 3% Estimate (minimum for PFF) could not be captured in the 2026 Budget due to the untimely presentation of the document to the State House of Assembly for Legislation and approval. However, the Ministry of Budget and Economic Planning has priotized the inclusion of the Head/Estimate in the Proposed 2026 Revised/Supplementary Budget. | i. Inclusion of a minimum 3% PFF Estimate in the Draft 2026 Revised / Supplimentary Budget for Legislation and other necessary approval. (Q2-Q3 2026) ii. Publication of the Draft 2026 Revised / Supplementary Budget containing the PFF Estimate on the State's official website in Q4 2026 (Subject to all necessary approvals).
|  | (i) to have an effective State invetsment promotion agency for service delivery to investors and targeted efforts towards attracting and retaining investment (ii) to ensure transparency, easier access to information, and participation for the stimulation of investments in the State; | C. Update and publish an inventory/database of all investment incentives (Federal and State) available in Ekiti State | 1. Improve transparency and ease of access to information on Ekiti State's investment environment for investors 2. Ensure at least 4 sessions are held in 2025 to engage with investors operating in Ekiti State, to discuss among others Business Environment Reforms and tax compliance. 3. Develop and implement an aftercare programe that caters to investors. | Director of Investment, Ekiti State Development and Investment Promotion Agency | Ministry of Industry, Trade and Investment; Bureau of Information and Communication Technology (BICT); Ministry of Finance & Economic Development and Ekiti State Internal Revenue Service | 8000000 | 2025-01-01 | 2025-12-31 | Completed
|  |  | D. Update EKDIPA's website with relevant information for investors, including access to credit | [6 empty] | Completed
|  |  | E. Organization of quarterly information sessions for investors by EKDIPA | [6 empty] | Completed
|  |  | F. Develop a dedicated aftercare unit within the IPA that provides ongoing support to existing investors, helping them expand, resolve operational challenges, and reinvest in Ekiti State | [6 empty] | Completed
4 | Increased Transparency of official fees and procedures | (i) This reform area will increase transparency of official fees and procedures focusing on key business environment enabling MDAs in Ekiti State; (ii) the reform will give easier access to regular information for greater regulatory efficiency, lower compliance costs and better regulatory quality; (iii) Reduce overlapping of licensing requirements; (iv) reduce potential discretionary behaviors | A.1. Sensitization on the schedule of trade related fees and levies on inter-state movement of goods | 1. Conduct advocacy meetings with groups and unions, emabark on distribution of leaflets and fliers at least twice a year to sensitize operators and provide comprehensive information on trade related fees and levies for inter-State movement of goods. 2. Publish monthly reports on GRM and SLA compliance on the State website. 3. The Office of the Head of Service will develop guidelines for Grievance Redress Mechanism (GRM) and ensure it has the required legal support | Office of the Head of Service, Director of Investment, Ekiti State Development and Investment Promotion Agency (EKDIPA), Director, Planning, Research and Statistics, Ekiti State Internal Revenue Services, Director of SME, Ministry of Industry, Trade and Investment | Ministry of Industry, Trade and Investment, Ministry of Justice, Ministry of Innovation, Science and Digital Economy, Ekiti State Development and Investment Promotion Agency (EKDIPA), Ministry of Physical Planning and Urban Development, Ekiti State Signage and Advertising Agency, Bureau of Land Services, and Ministry of Industry, Trade and Investment; Secretary to the State Government; Bureau of Information and Communication Technology; Ministry of Information | 5,000,000 | 2025-01-01 | 2025-12-31 | Completed |  | This action will be repeated in 2026 for further impact
|  |  | A.2 Develop, publish and implement service level agreements (SLAs) in the 5 BEE MDAs | [6 empty] | Completed
|  |  | A.3 Online publication of a monthly report on the operation and implementation of the GRM and SLAs in the 5 BEE MDAs | [6 empty] | Completed
|  |  | A.4. Develop State Grievance Redress Mechanism with legal backing | [6 empty] | Delayed | The State Centralized Grievance Redress Mechanism has been developed and ready for EXCO ratification. The delay was due to administrative review and approval processes required for Executive Order. | The executive order was developed in first quarter of 2026, it has been finalised and is currently awaiting the approval of The Governor. It is expected that the approval process will be concluded upon the Governor's consideration in the third quater. Actionable steps to be taken are: i. Obtain the approval and signing of the Executive Order by His Excellency, the Governor of Ekiti State; ( Subject to His Excellency work schedule, Tentatovely scheduked for July 2026) ii. Secure Executive Council acknowledgement and communicate the approved framework to all MDAs;(Subject to EXCO meeting, Tentatively scheduled for July 2026) iii. Officially launch the State Centralised Grievance Redress Mechanism; ( Immediately the bill is approved by te EXCO, Tentatively August 2026) iv. Designate GRM focal persons across MDAs (September 2026); v. Conduct stakeholder sensitization and awareness programms (September 2026); vi. Build the capacity of relevant officers responsible for grievance management; vii.Deploy and operationalize the centalsed grievance management and reporting structure; viii. Commence monitoring, evaluation and periodic reporting on grievance resolution performance across MDAs.
5 | Domestic and external trade competitiveness | Promote export activities and position Ekiti State as an attractive export hub for investors through the implementation of the State Committee on Export Promotion (SCEP)'s mandate | A.1.Upgrade the state’s transport infrastructure (roads, rail, and air) to ensure efficient movement of goods from production areas to export terminals. This should include connecting key agricultural areas to markets and ports. | 1. Sensitization campaigns will be coordinated and carried out by the SCEP, EKDIPA and Ministry of Trade to attract new Exporters with incentives put in place to help Export business in the State 2. Topics should include export procedures, international market entry strategies, compliance with international standards, and export financing options | State Committee on Export Promotion; Director SME, Ministry of Industry, Trade and Investment | Ministry of Budget and Economic Planning, Ministry of Finance & Economic Development, Nigerian Export Promotion Council, Ministry of Agriculture and Food Security, Bureau of Information and Communication Technology (BICT), Ekiti State Internal Revenue Services, Ministry of Information | 2500000 | 2025-01-01 | 2025-12-31 | Completed
|  |  | A.2.Conduct regular capacity-building workshops and seminars for small and medium-sized enterprises (SMEs) on how to become export-ready | [6 empty] | Completed |  | The action will be repeated in 2026 for further impact
|  |  | A.3.Partner with organizations such as the Nigerian Export Promotion Council (NEPC) and international agencies to offer technical assistance to businesses on packaging, labeling, and certification required for international markets. | [6 empty] | Completed
|  |  | A.4 Increase the number of firms with export certificates from Nigerian Export Promotion Council (NEPC) attracted to Ekiti State by 50% | [6 empty] | Completed
|  |  | A.5. Work with financial institutions, including the Export-Import Bank of Nigeria (NEXIM) and other development finance institutions, to create accessible financing schemes for businesses in Ekiti State that are ready to export | [6 empty] | Completed
|  |  | A.6. Encourage businesses to utilize e-commerce platforms to sell products to international buyers. Provide training and support for online sales, digital marketing, and international shipping logistics. | [6 empty] | Completed
6 | Simplification of State and Local Business Tax Regimes | This reform is aimed at making it easy to understand and make payment for tax in Ekiti State | A.1. Conduct regular public awareness campaigns and training sessions to educate businesses about their tax obligations, filing procedures, and the benefits of compliance | 1. Ensure electronic payment of all State-level and local government taxes, levies and fees from business (with adoption of at least 75% of State collection of taxes, levies and fees from businesses) 2. Generate harmonized Demand Notice; print and serve consolidated Demand Notices | Director, Legal Matters, Ekiti State Internal Revenue Services; Director, Planning, Research and Statistics, Ekiti State Internal Revenue Services; | Ministry of Finance, Ministry of Justice and Ekiti State House of Assembly, Ministry of Local Government, Ministry of Industry, Trade and Investment, Ministry of Infrastructure and Public Utilties, | Not Applicable | 2025-01-01 | 2025-12-31 | Completed
|  |  | B.Enable businesses, especially small enterprises, to pay taxes using mobile payment platforms (e.g., USSD codes, mobile apps) that are convenient and accessible across the state | [6 empty] | Completed
|  |  | B.1 Raise consolidated demand notices for all business-related local government charges/fees/taxes | [6 empty] | Completed
|  |  | C. Automate the process for the collection of taxes, levies and fees from businesses and generate e-receipt (QR code or unique payment ID) for all BEE MDAs | [6 empty] | Completed
7 | Quick determination of commercial disputes | This reform area will improve the State Judiciary and strengthen access to an efficient commercial justice system | A.1 publish the Small Claims Courts Monthly Performance Reports | The Judiciary will provide and publish a monthly small claims court performance report: - ensure at least 75% of cases are disposed of within 60 days - ensure 75% of the judgments are executed within 30 days | Ekiti State Judiciary | Ministry of Justice, Bureau of Information, Communication and Technology (BICT) | Not Applicable | 2025-01-01 | 2025-12-31 | Completed