## corrected to be completed
SPHCDA WORK PLAN 2025
s/n | Activity | Timeline | Indicator | Target | Output | Outcome | Programme Description /Code | Envelop Ceiling MTEF | Implication
1 | quaterly fueling of the cold store to support the existing power arrangement. | Jan-Dec | Availability of electricity suppily | 100% Potency of vaccine | Power supply | avaialbility of potent vaccine for good serivce delivery | Facility eletrification, water and sanitation (040503) | 0 | 12000000
2 | Purchase of cold chain equipment and Maintanance of cold chain Devices | Jan-Dec | working optimally | 70% Effective service delivery | Good service delivery | enhance efficiency | Vaccine supply chain (040602) | 10000000 | 13000000
3 | Monitoring and supportive supervision and data collation | Jan-Dec | Number of supportive supervision visits | 12 visits completed | Supervision reports produced | Improved compliance with standards | Monitoring and evaluation (040704) | 0 | 2000000
4 | Proper and effective disposal of immunisation wastes including safety boxes at state and local cold stores | Jan-Dec | Immunization coverage (%) | ≥95% coverage | Children immunized | Reduced vaccine-preventable diseases | Facility eletrification, water and sanitation (040503) | 0 | 25000000
5 | Logistics for contigency expenses on vaccine movement and loading/offloading of vaccines and commodities at State Cold Chain Store | Jan-Dec | improved working condition | 100% availability of vaccine | availability of vaccine in the cold chain store | constact supply of vaccine | Planned Preventive Maintenance (040502) | 0 | 3600000
6 | Conduct of quaterly planned preventive maintenance in 16, LGA cold stores, 241 facilities with SDD freezers, and the state cold store | Jan-Dec | Number of quaterly planned across 16 LGA | 100% of planned activity completed | Good service delivery | Improved Vacine store | Planned Preventive Maintenance (040502) | 0 | 5000000
7 | Conduct monthly disposal of waste at the state level (incineration of needles and boil and bury of empty and expired vials) | Jan-Dec | Number of waste disposal conducted | 100% of planned activity completed | report of evidence of waste desposal | Prevention of service delivery | Planned Preventive Maintenance (040502) | 0 | 10000000
8 | Capacity building of TBAs on early idetification risk of pregnancy and prompt referral | Jan -June | Increased maternal mortality rate | 20% TBAs trained | at least 64 TBAs will be trained high risk identification and prompt referrel | The training will enhance TBAs on how to refer promptly | Reproductive, Maternal and Neonata Health (04301) | 0 | 20000000
9 | Procurement of Mama kits | Jan -June | to increase patronage of pregnant women in all health facilites | 50% To support pregnant women and to increase facility delivery | at least 2000 of pregnant mothers received mama kit for good delivery | facility delivery increased | community Interventions (040201) | 12000000 | 20000000
10 | Capacity building of TBAs on early idetification risk of pregnancy and prompt referral | Jan -June | Increased maternal mortality rate | 20% TBAs trained | at least 64 TBAs will be trained high risk identification and prompt referrel | The training will enhance TBAs on how to refer promptly | Reproductive, Maternal and Neonata Health (04301) | 0 | 25000000
11 | Training and Develop the REW microplan in all the 317 facilities offering RI and quarterly update, verify and validate the REW microplan, to identify the strategies, numbers of vaccinations session and resources mapping for ROUTINE IMMUNIZATION activities in all 2917 settlement of the state. | January, April, July & Oct | Number of health facilities with REW?REC microplan verified and validated | 100% | improved knowledge on the concept of REW/REC and Availability of updated microplan | Availability of Comprehensive REW/REC captured in wards and settlement microplan | Survey and facility assessments (040702) | 0 | 15000000
12 | support the 317 facilities offering RI for the conduct of weekly outreach sessions visiting settlements above 2km to the facility | January to December | percentage of planned sessions conducted | 100% | increase in the of children vaccinated | Reduction in the no of unimmunized and drop outs and increase in % coverage, | Routine Information system (040701) | 0 | 75000000
13 | Purchase of Adverse effects following Immunization (AEFI )kit for routine immunization of under 23 months across the 16 LGAs and LCDAs In all 317 health facilities offering Routine Immunization | Jan- Dec | % of facilities with AEFI KIT | 319 PHC health facilities | Prompt treatment of reported AEFI cases at the facility level | Reductions in the numbers of untreated AEFI cases at the facility level | Routine Information system (040701) | 0 | 10020000
14 | Conduct defaulters tracking in all the 317 facilities offering RI and mobilization of elligible children to the facility by engaging 317 defaulters tracker using defaulter's tracking slip,phoning, bulk SMS and home visiting | January to December | % of drop out and unimmunized | 100% | No of Newborn and defaulters tracked | completion of vaccination schedule by targeted age group | community Interventions (040201) | 0 | 24000000
15 | Conduct monthly supportive supervision by 32 state RI supervisors in all the 317 facilities offering RI across the 16 LGAs in Ekiti State at two visit per month | January to December | Number of supportive supervision planned and conducted | 100% | Improvement in RI service delivery | Improvement in RI coverage | Monitoring and evaluation (040704) | 4500000 | 8000000
16 | Conduct a 5-day house to house enumeration of under five children in all the 2917 settlement across the 16 LGAs in the state utilizing 1408 team of 3 personnel | Jan - Dec | Number conducted for enumeration | 100% of planned activity completed | report of numbers of house conducted | Reduced vaccine-preventable diseases | Legal, policy, regulations and standards, guidelines and protocols development and reviews (040101) | 0
17 | A day orientation of 1408 enumeration team of 3 personnel about the strategies and data tools that will be deployed for the enumeration | Jan - Dec | Number oriented | 100% of planned activity completed | report oriented conducted | Reduced vaccine-preventable diseases | Legal, policy, regulations and standards, guidelines and protocols development and reviews (040101) | 0 | 2500000
18 | Conduct of a 7-day Big-Catch Up Campaign in 7 prioritised LGAs in Ekiti State with 140 teams of 6 personnel per team | Jan - Dec | Number of LGAs conducted for compaign | 100% of planned activity completed | Numbers of Big catch up reported | Reduced vaccine-preventable diseases | Legal, policy, regulations and standards, guidelines and protocols development and reviews (040101) | 0 | 4200000
19 | Selection and inauguration of 1 vaccine champion per ward in all the 177 wards in the state | Jan - Dec | Immunization coverage (%) | ≥95% coverage | Children immunized | Reduced vaccine-preventable diseases | Legal, policy, regulations and standards, guidelines and protocols development and reviews (040101) | 0 | 1200000
20 | Conduct quarterly community reconciliation meeting with the 5 member of the community reconciliation committee in 177 wards to addresss isssues of vaccine hesitancy,rejection and non compliance. | Jan - Dec | Number of coordination meetings held | 4 quarterly meetings | Meeting resolutions implemented | Strengthened coordination | Legal, policy, regulations and standards, guidelines and protocols development and reviews (040101) | 0 | 2300000
21 | Purchase of project vehicle for effective monitoring | Jan - Dec | Number of supportive supervision visits | 12 visits completed | Supervision reports produced | Improved compliance with standards | Functional Health Facilities (040501) | 0 | 65500000
22 | Conduct Monthly data validation meeting in 16 LGAs with 317 RI focals, 16 CCO, 16 LIO and 16 state data officers | Jan - Dec | Number of coordination meetings held | 4 quarterly meetings | Meeting resolutions implemented | Strengthened coordination | Monitoring and evaluation (040704)M | 0 | 1500000
23 | Conduct quaterly data quality assessment in 317 facilities offering Routine Immunization by 32 data officers | Jan - Dec | number of Immunization coverage (%) | ≥95% coverage | Number Children immunized | Reduced vaccine-preventable diseases | Monitoring and evaluation(040704) | 0 | 2500000
24 | Support the State and LGA for monthly and quartely vaccine pull from the National strategic and state cold store and reverse Logistics | Jan - Dec | number of Immunization coverage (%) | ≥95% coverage | Number Children immunized | Reduced vaccine-preventable diseases | Vaccine supply chain (040602) | 0 | 4200000
25 | Support the 317 facilities offering RI for vaccine collection from the LGA cold store and reverse logistics | Jan - Dec | number of Immunization coverage (%) | ≥95% coverage | Number Children immunized | Reduced vaccine-preventable diseases | Vaccine supply chain (040602) | 0 | 1200000
26 | Conduct of bi-annual Maternal, Newborn and Child Health Week (MNCHW) | Jan - Dec | Activity implementation rate (%) | 100% of planned activity completed | Planned activity implemented | Improved programme performance | Nutrition (040306) | 0 | 2300000
27 | Commemoration of World Breastfeeding Week (Symposium, outreach) | Aug | Number of women of child bearing age sensitized | 22% of T.P | Sensitization of at least 85% of the target | Reduction in infant mortality due to poor infant feeding practices | Nutrition (040306) | 0 | 15000000
28 | 3 days training of 177 health workers acoss the 3 senatorial districts on Maternal, Infant and Young Child Nutrition (MIYCN) | Jan - Dec | Number of health workers trained | Train 100 health workers by Q4 | Health workers trained | Improved staff capacity | Nutrition (040306) | 0 | 2500000
29 | Conduct of 2 rounds of supportive supervision on effective growth monitoring, promotion and nutrition services in 177 wards across the 16 LGAS | Jan - Dec | Number of supportive supervision visits | 12 visits completed | Supervision reports produced | Improved compliance with standards | Nutrition (040306) | 0 | 4200000
30 | Food demonstration activities across 177 health facilities in Ekiti State | Jan - Dec | Number of health Facilities carry out food demonstration | 100% planned | report of Facility conducted | Improved programme performance | Nutrition (040306) | 5000000 | 6000000
31 | 2 days training of 177 health workers acoss the 3 senatorial districts on Integrated Management of Acute Malnutrition (IMAM) | Jan - Dec | Number of health workers trained | Train 100 health workers by Q4 | Health workers trained | Improved staff capacity | Nutrition (040306) | 0 | 2300000
32 | Purchase of Drugs and Consumables and other activities for implementation of Supplemental immunization activities for under 5 children in Ekiti State | Jan-Dec | % of under 5 covered during SIA | 20% of Total Population | Boosting the immunity of Under 5 children against vaccine preventable disease | Achievement of herd immunity in the state | Sustainable drug supply (040601) | 18500000 | 26000000
33 | Active case search of malnourished children across 16 LGAs in Ekiti State | Jan - Dec | Number of malnourished finds | 100% of planned activity completed | report of malnourished detected | reduction of malnutrition in the State | Nutrition (040306) | 0 | 2500000
34 | Nutrition Project: purchase of health and medical equipment | Jan - Dec | Activity implementation rate (%) | 100% of planned activity completed | Planned activity implemented | Improved programme performance | Nutrition (040306) | 0 | 4200000
35 | Conduct sensitisation training on Leprosy and Buruli Ulcer for Medical students/ Nursing school/ college of health Technology. Targeting 300 participants | Jan - Dec | No of school visited and No of Student trained | At least 1 medical school,1 school of Nursing School and I college of health Technology school | sensitisation Training conducted | Increase knowledge of Medical /Nursing and Health Tech student on Leprosy and BU case finding. | community Interventions (040201) | 0 | 1200000
36 | Conduct 3 days National TB testing week | Jan, May | No of outreaches conducted and sensitisation campaign carried out and No of health facilities that has access to IEC materials | At least 3 Outreaches per LGA and world Leprosy conducted | Childhood TB testing week conducted and world Leprosy conducted | Increase Childhood TB and Leprosy case detection and access to quality treatment services | community Interventions (040201) | 0 | 2300000
37 | Provision of Transport support to trace Contact of 500 Index TB case and reversal contact tracing of diagnosed children with TB | Jan-Dec | Number of diagnosed children traced | at least 90% | report of the number traced | Reduction of TB in children | community Interventions (040201) | 0 | 2500000
38 | Conduct 3 days National Childhood TB week | Jan-Dec | Number of participants | 100% of planned | Report of TB week Conducted | Reduction of TB in children | community Interventions (040201) | 0 | 4200000
39 | Conduct Quaterly TB outreach ( 1 per LGA in a quarter )utilizing portable disgital x-rays and rapid molecular testing platforms | Jan-Dec | Number of outreach conducted | 100% of planned | Report of TB outreach Conducted | Reduction of TB in children | community Interventions (040201) | 0 | 1200000
40 | Commenmoration of World TB day | Jan-Dec | nunmber of World TB day commenmorative | at least 2,000 people | TB screening conduct | increased public awareness of TB | community Interventions (040201) | 0 | 2300000
41 | One day Capacity Building of 100 DOTS staff on Adherence Counselling | Jan-Dec | Number of participants trained | 100% of planned | Trained report | Improved service delivery | planned Preventive Maintenance (040502) | 0 | 2500000
42 | Establish defaulter tracking system across 16 LGA with provision of communication ( 2000) /Transportation allowance ( 5000)for DOTS Staff on no of loss to follow up patients tracked and bring back to treatment ( Target 5 % of total case registered annualy) | Jan-Dec | Activity implementation rate (%) | 100% of planned activity completed | Planned activity implemented | Improved programme performance | community Interventions (040201) | 0 | 4200000
43 | Establishaditinal two DRTB OPD clinics in 2 LGA to complement 5 existing one. | Jan-Dec | Activity implementation rate (%) | 100% of planned activity completed | Planned activity implemented | Improved programme performance | community Interventions (040201) | 0 | 1200000
44 | Testing and Sensitization on HIV in higher Institutions in the State | Jan-Dec | Activity implementation rate (%) | 100% of planned activity completed | Planned activity implemented | Improved programme performance | community Interventions (040201) | 5000000 | 2300000
45 | Procurement of HIV Test kit | Jan-Dec | Activity implementation rate (%) | 100% of planned activity completed | Planned activity implemented | Improved programme performance | community Interventions (040201) | 0 | 2500000
46 | Commemmoration of World Hepatitis Day | Jan-Dec | Activity implementation rate (%) | 100% of planned activity completed | Planned activity implemented | Improved programme performance | community Interventions (040201) | 0 | 4200000
47 | Hold Bimonthly State/LGA data review meeting | Jan-Dec | Number of coordination meetings held | 4 quarterly meetings | Meeting resolutions implemented | Strengthened coordination | Health sector coordination mechanisms (040103) | 0 | 1200000
48 | Conduct Bi-monthly Data Quality Assurance to Comprehensive and Spokes Sites to ensure quality of data generated and reported on NDARS (National Data Reporting System) | Jan-Dec | % number of NDARS generated | 100% | Data Report | Improved data quality Assurance | community Interventions (040201) | 0 | 2300000
49 | Conduct 2 days quarterly targetted outreaches to 5 communities with low rate of HIV testing and treatment gap | Jan-Dec | Number of outreached target | at least 80% | Gaps identify | Reduction of HIV in the State | community Interventions (040201) | 0 | 2500000
50 | Conduct a 5 day quarterly Intergrated Supportive Supervision to BHCPF Health Facilities by 40 BHCPF State team members. | Jan-Dec | % of PHCs that the state visited for ISS | 100% | Integrated Supportive supervision to 177 BHCPF facilities | Quality service delivery | Integrated Supportive Supervision (040104) | 0 | 4200000
51 | Conduct a day monthly BHCPF mentoring visits to 177 eligible PHC s by 80 mentors, monitored by 5 state core team members | Jan-Dec | % of PHCs visited by a mentor | 100% | To conduct monthly viisit to to BHCPF facilities | Quality service delivery | Monitoring and evaluation (040704) | 0 | 1200000
52 | Conduct bi-annual one day non-residential BHCPF gateway Stakeholders meeting on the implementation status for 45 person | Jan-Dec | No of BHCPF gateway meeting done with minutes of meetings | 100% | To examine and review progress and challenges in BHCPF implementation towards achieving program objectives. | Ensure quality service delivery | Health sector coordination mechanisms (040103) | 0 | 2300000
53 | Mass administration of medicines for Onchocerciasis, schistosomiasis and soil transmitted helminths | Jan-Dec | Percentage coverage | 80% treatment coverage | all eligible population treated with ivermectin | reduction in morbidity | Community Interventions (040201) | 0 | 50000000
54 | Mass administration of medicines for schistosomiasis and soil transmitted helminths | Jan-Dec | Percentage coverage | 80% treatment coverage | all eligible treated with mebendazole | reduction in morbidity | Community Interventions (040201) | 0 | 30000000
55 | Conduct 2 days skin camp in collaboration with NTD in 8 LGA with report of Leprosy and BU | Jan-Dec | Activity implementation rate (%) | 100% of planned activity completed | Planned activity implemented | Improved programme performance | Community Interventions (040201) | 0 | 2500000
56 | Constitute and conduct quarterly AIDs, TBL, Malaria & NTDs (ATM-NTDs) technical working group (TWG) meeting | Jan-Dec | Number of coordination meetings held | 4 quarterly meetings | Meeting resolutions implemented | Strengthened coordination | Health sector coordination mechanisms (040103) | 0 | 4200000
57 | Conduct 2024 review and 2025 state level planning meeting of NTDS activities among 16 State NTDs Officers and 32 LGA - NTDs Officers | Jan-Dec | Number of coordination meetings held | 4 quarterly meetings | Meeting resolutions implemented | Strengthened coordination | Community Interventions (040201) | 0 | 1200000
58 | Conduct 2025 world NTDs day celebration in Ekiti State with the attendance of 100 stakeholders | Jan-Dec | Activity implementation rate (%) | 100% of planned activity completed | Planned activity implemented | Improved programme performance | Community Interventions (040201) | 0 | 2300000
59 | Conduct training of 32 state and 32 LGA officers on mass administration of medicines for onchocerciasis, Schistosomiasis and soil transmitted helminthes | Jan-Dec | Number of health workers trained | Train 100 health workers by Q4 | Health workers trained | Improved staff capacity | Community Interventions (040201) | 0 | 2500000
60 | Conduct training of 900 FLHWs and 8500 CDDs and supervision of mass administration of medicines for onchocerciasis, schistosomuiasis and soil transmitted helminmthes | Jan-Dec | Number of health workers trained | Train 100 health workers by Q4 | Health workers trained | Improved staff capacity | Community Interventions (040201) | 0 | 4200000
61 | To conduct epidemiological assessment for schistosomiasis and Soil Transmkitted Helminthes among school aged children with 30 stool and urine samples collected per ward | Jan-Dec | Number conducted | 100% of planned activity completed | Planned activity implemented | Improved programme performance | Community Interventions (040201) | 0 | 1200000
62 | carry out morbidity management and disability prevention for 50 patients with lymphoedema and hydrocele on quarterly basis | Jan-Dec | Number of patients prevented | 100% of planned activity completed | Planned activity implemented | Improved programme performance | Community Interventions (040201) | 0 | 2300000
63 | Capacity Building For Stakeholders on Development of Minimum Service Package according to PHCUOR of National Primary Health Care Across the State | Jan-Dec | To strengthening the health service delivery across the PHC facilities level | 100% | To develop minimum service packages for service delivery for the PHC in the State. | enhance performance and progress of service delivery in health facilities | Health sector coordination mechanisms (040103) | 10000000 | 50000000
64 | Bi-annual review meeting of HRH with Stateholder and 16 LGAs Focal to discuss Root Cause Anlysis of HRH | Jan-Oct | Number of coordination meetings held | 4 quarterly meetings | Meeting resolutions implemented | Strengthened coordination | Health sector coordination mechanisms (040103) | 0 | 2000000
65 | Monthly PHC integrated review meeting | Jan Dec | strengthening PHC integration for optimal service delivery | at least 100% covarage in interventions | To address identified gaps in all PHC programs | Improved access to services performance | Health sector coordination mechanisms (040103) | 0 | 15000000
66 | Training of HRH focal person across the 16LGAs level and stakerholders on the use of current version of NPHCDA PHC-IS Primary Health Care Information System platform | Jan Dec | Number of participants trained | Train 100 health workers by Q4 | Health workers trained | Improved staff capacity | Health sector coordination mechanisms (040103) | 0 | 4000000
67 | Renovation of PHC Facilities across the state | Jan Dec | 100% | availability of PHC facilites | strenghtening of Health service | improvement of service delivery | Functional Health Facilities (040501) | 10000000 | 4200000
68 | Purchase of Bluetooth speakers for 177 wards and megaphones batteries | Jan Dec | 80% of existing bluetooth | LGA Hes | Availability of bluetooth | To create awareness aboutPHC services | Planned Preventive Maintenance (040502) | 7860093.59 | 1200000
69 | Production of IEC/BCC/Other material and airing of Radio jingles/PSA on TV/ TV/radio appearnace etc | Jan Dec | 100% TV, radio appearance | Paopulace | To disseminate information on radio | To sensitize the populace about PHC services | Planned Preventive Maintenance (040502) | 0 | 2300000
70 | One-day Capacity building of 200 HW on Interpersonal communication and counselling to improve quality of care and service delivery. | Jan Dec | Number of health workers trained | 100% of planned activity completed | Planned activity implemented | Improved programme performance | Planned Preventive Maintenance (040502) | 0 | 3500000
71 | Train 50 FLHWs & 250 CDDs and supervise hygiene promotion activities at the community level | Jan Dec | Number of health workers trained | Train 100 health workers by Q4 | Health workers trained | Improved staff capacity | Planned Preventive Maintenance (040502) | 0 | 4200000
72 | One day Advocacy meeting and awareness creation for 100 community leaders/gatekeepers on Implementation and scale up the community approach to improving access to TPT. | Jan Dec | Number of coordination meetings held | 4 quarterly meetings | Meeting resolutions implemented | Strengthened coordination | Planned Preventive Maintenance (040502) | 0 | 1200000
TOTAL | [7 empty] | 82860093.59 | 650020000

## Sheet2 (2)
s/n | Activity | Timeline | How | Indicator | Programme Description /Code | Envelop ceiling MTEF | TARGET | Output | Outcome | Estimate Cost Implication
COLD CHAIN
1 | quaterly fueling of the cold store to support the existing power arrangement. | Jan-Dec | through vendor and direct purchase | Availability of electricity suppily | Facility eletrification, water and sanitation (040503) |  | 100% Potency of vaccine | Power supply | avaialbility of potent vaccine for good serivce delivery | 12000000
| Purchase of cold chain equipment and Maintanance of cold chain Devices | Jan-Dec | through servicing | working optimally | Vaccine supply chain (040602) | 10000000 | 70% Effective service delivery | Good service delivery | enhance efficiency | 6000000
| Monitoring and supportive supervision and data collation | Jan-Dec | Visiting the health facilities and Collection of data in all LGAs | Availability of vaccines and cold chain equipments and Effective service deliveries | Monitoring and evaluation (040704) | 0 | 100% 329 Staffing Health Facilities and Timely reporting | Availability of vaccine and follow up activities | quality delivery and accuracy of data collection | 3000000
| Proper and effective disposal of immunisation wastes including safety boxes at state and local cold stores | Jan -Dec | vendors | safe working condition | Planned Preventive Maintenance (040502) | 0 | 100% of waste generated | global best practices | effective IPC | 2800000
| Logistics for contigency expenses on vaccine movement and loading/offloading of vaccines and commodities at State Cold Chain Store | Ja-Dec | contractual | improved working condition | Planned Preventive Maintenance (040502) | 0 | 100% availability of vaccine | availability of vaccine in the cold chain store | constact supply of vaccine | 3600000
| Conduct of quaterly planned preventive maintenance in 16, LGA cold stores, 241 facilities with SDD freezers, and the state cold store | Jan-Dec | PHYSICAL | To improve cold chain store | Sustainable drug supply
| Conduct monthly disposal of waste at the state level (incineration of needles and boil and bury of empty and expired vials) | Jan -Dec | PHYSICAL | monthly disposable of waste in the cold chain | vaccines supply to cold chain (040602) | 0
REPRODUCTIVE HEALTH
2 | Commemoration of safe motherhood day celebration | April 22nd | 1 week celebration | women of child bearing age were sensitized on early ANC booking and facility delivery | Reproductive, Maternal and Neonata Health (04301) | 0 | % womem of child bearing age | at least 200 of women of child bearing age | awareness creation | 5000000
| Capacity building for CHOs/CHEWs on Modified Life saving Skill | Jan -Nov | 10 days residential training | Knowledge deficit of CHOs/CHEWs on MLSS | Reproductive, Maternal and Neonata Health (04301) | 0 | 30% CHOs/CHEWs | at least 32 of CHOs/CHEWs across the 16LGA | CHOs/CHEWs have knowledge on modified life saving skill | 20000000
| Procurement of Mama kits | Jan -June | purchase of Mama kits to assist pregnant women | to increase patronage of pregnant women in all health facilites | community Interventions (040201) | 12000000 | 50% To support pregnant women and to increase facility delivery | at least 2000 of pregnant mothers received mama kit for good delivery | facility delivery increased | 60000000
| Capacity building of TBAs on early idetification risk of pregnancy and prompt referral | Jan -June | 3days non residential training for TBAs | Increased maternal mortality rate | Reproductive, Maternal and Neonata Health (04301) | 0 | 20% TBAs trained | at least 64 TBAs will be trained high risk identification and prompt referrel | The training will enhance TBAs on how to refer promptly | 40000000
IMMUNIZATION
3 | Training on REW/REC microplan and Update,verify and validate the REW Microplan and master list of settlements | January, April, July & Oct | Physical training and Visit to the 16LGA | Number of health facilities with REW?REC microplan verified and validated | Survey and facility assessments (040702) | 0 | 100% | improved knowledge on the concept of REW/REC and Availability of updated microplan | Availability of Comprehensive REW/REC captured in wards and settlement microplan | 15000000
4 | Conduct RI Sessions (at least 4 fixed and 2 Outreach /month) in all health facilities; | January to December | Provisions of RI services using the fixed and outreach strategies | percentage of planned sessions conducted | Routine Information system (040701) | 0 | 100% | increase in the of children vaccinated | Reduction in the no of unimmunized and drop outs and increase in % coverage, | 75000000
| Purchase of Adverse effects following Immunization (AEFI )kit for routine immunization of under 23 months across the 16 LGAs and LCDAs In all 317 health facilities offering Routine Immunization | Jan- Dec | supplies to all RI facilities | % of facilities with AEFI KIT | Routine Information system (040701) | 0 | 319 PHC health facilities | Prompt treatment of reported AEFI cases at the facility level | Reductions in the numbers of untreated AEFI cases at the facility level | 19020000
| Purchase of Drugs and Consumables and other activities for implementation of Supplemental immunization activities for under 5 children in Ekiti State | Jan-Dec | Campaign mass vaccination and outbreak responses | % of under 5 covered during SIA | Sustainable drug supply (040601) | 18500000 | 20% of Total Population | Boosting the immunity of Under 5 children against vaccine preventable disease | Achievement of herd immunity in the state | 48000000
5 | Tracking of defaulters through the use of baby tracking slips, phoning and home visiting, VCM/WDC, RI focal/ward focal persons, bulk SMS | January to December | Phone calls, house to house visit | % of drop out and unimmunized | community Interventions (040201) | 0 | 100% | No of Newborn and defaulters tracked | completion of vaccination schedule by targeted age group | 37000000
6 | RI supportive suppervision | January to December | Visit to the 16LGA | Number of supportive supervision planned and conducted | Monitoring and evaluation (040704) | 0 | 100% | Improvement in RI service delivery | Improvement in RI coverage | 11520000
| Tranning of Health workers on RI guide | April | Physical training of 640 health workers on RI guide | reduction in child mortality due to preventable diseases | Legal, policy, regulations and standards, guidelines and protocols development and reviews (040101) | 0 | 100% | Improvement in quality of RI services rendered | enhance service delivery | 25000000
| Conduct a 5-day house to house enumeration of under five children in all the 2917 settlement across the 16 LGAs in the state utilizing 1408 team of 3 personnel | Jan Dec | Visit to the 16LGA |  | Routine Information system (040701)
| A day orientation of 1408 enumeration team of 3 personnel about the strategies and data tools that will be deployed for the enumeration | Jan Dec | Enumeration and strategies of data tools |  | community Interventions (040201)
| Conduct of a 7-day Big-Catch Up Campaign in 7 prioritised LGAs in Ekiti State with 140 teams of 6 personnel per team | Jan Dec | physical |  | Health sector coordination mechanisms(040103)
| Develop the REW microplan in all the 317 facilities offering RI and quarterly update, verify and validate the REW microplan, to identify the strategies, numbers of vaccinations session and resources mapping for ROUTINE IMMUNIZATION activities in all 2917 settlement of the state. | Jan Dec |  | routine immunization activities | Routine Information System(040701)
| Conduct monthly supportive supervision by 32 state RI supervisors in all the 317 facilities offering RI across the 16 LGAs in Ekiti State at two visit per month | Jan Dec | physical | Supplies to all routine immunization | Routine Information System(040701)
| Conduct defaulters tracking in all the 317 facilities offering RI and mobilization of elligible children to the facility by engaging 317 defaulters tracker using defaulter's tracking slip,phoning, bulk SMS and home visiting | Jan Dec | Campaign mass vaccination and outbreak responses | mobilizing of eligible children to the facility | Community structures(040202)
| support the 317 facilities offering RI for the conduct of weekly outreach sessions visiting settlements above 2km to the facility | Jan Dec | weekly outreach sessions | routine immunization activities | Community engagement and participation in health(0402)
| Selection and inauguration of 1 vaccine champion per ward in all the 177 wards in the state | Jan Dec | campaign mass vaccination in all the wards | launching of 1 vaccine in all the 177 wards | community Interventions (040201)
| Conduct quarterly community reconciliation meeting with the 5 member of the community reconciliation committee in 177 wards to addresss isssues of vaccine hesitancy,rejection and non compliance. | Jan Dec | physical | meeting with the 5 members of the community committee | Community engagement and participation in health(0402)
| Purchase of project vehicle for effective monitoring | Jan Dec | physical | easier way of working condition | Monitoring and evaluation(040704)
| Conduct Monthly data validation meeting in 16 LGAs with 317 RI focals, 16 CCO, 16 LIO and 16 state data officers | Jan Dec | physical | monthly data assessment in 16 LGA | Survey and facility Accessments(040702)
| Conduct quaterly data quality assessment in 317 facilities offering Routine Immunization by 32 data officers | Jan Dec | physical | Conduction of data quality through RI | Routine information system(040701)
| Support the state for possible quartely vaccine pull from the National strategic cold store | Jan Dec | contractual | Vaccines flag off from the national level | Vaccines supply chain(040602)
| Support the LGAs for monthly vaccine pull from the State cold store and reverse logistics | Jan Dec | contractual | financing the LGA for the monthly vaccine | Vaccines supply chain(040602)
| Support the 317 facilities offering RI for vaccine collection from the LGA cold store and reverse logistics | Jan Dec | vendors | reaching out to all the 317 RI for collection of vaccines from the LGA | Surveys and facility assessment(040702)
NUTRITION
7 | Commemoration of World Obesity Day | March | Sensitization/awareness creation on Obesity | % of people sensitized on Obesity | Nutrition (040306) |  | 70% of total population | Awareness creation for at least 50% of the target | Reduction in mortality resulting from Obesity | 5000000
8 | Maternal Newborn and Child Health Week (Bi-annual) | May/June Nov/Dec | Vitamin A Supplementation for 6-59 months children | % of Children 6-59 months supplemented with Vit.A | child health(040302) |  | 18 % of T.P. | Supplementation of at least 80 % of the target | Micronutrient deficiency prevented | 85000000
|  |  | Deworming Tablets administration for 12-59 months children | % of Children 12-59 months dewormed |  |  | 16 % of T.P. | Increase in coverage to at least 80 % | Prevention of parasitic worm infections
|  |  | Malnutrition Screening for 6-59 months children | % of Children 6-59 months screened for malnutrition |  |  | 5% of T.P. | Malnutrition Screening for at least 80% of the target | Decrease in infant mortality due to malnutrition
|  |  | Multiple micronutrient supplementation (MMS) for pregnant women | % of Pregnant women supplemented with MMS |  |  | 20 % of T.P. | Supplementation of at least 70 % of the target | Improved maternal nutritional status
|  |  | Routine Immunization (RI) antigen for children between 0-15 months | % of Children under 5 vaccinated |  |  | 20 % of T.P. | Vaccination of at least 80 % of the target | Reduction in outbreak of vaccine preventable diseases
9 | Commemoration of World Breastfeeding Week | Aug | Sensitization of women on exclusive breastfeeding (EBF) and continued breastfeeding | Number of women of child bearing age sensitized | Nutrition (040306) |  | 22% of T.P | Sensitization of at least 85% of the target | Reduction in infant mortality due to poor infant feeding practices | 15000000
10 | MNCH Routine Intervention on food demonstration | Jan-Dec | Food demonstration practices resucitation in 326 health facilities offering nutrition services | Number of mothers counselled on Infant and young child feeding practices | Nutrition (040306) | 5000000 | 22% of T.P | 80% of the target counselled | Child malnutrition and mortality is reduced | 6500000
11 | Integrated Supportive Supervision (2 rounds) | April/ October | Supportive supervision on nutrition activities across 160 health facilities in each round in Ekiti State | Number of health facilities visited for supportive supervision/on-the-job training on nutrition activities | Integrated Supportive Supervision (040104) |  | 320 health facilities | 100% of the target visited | Enhanced communication and improved orientation for nutrition/health workers on nutrition activities for quality service delivery | 12000000
| Conduct of bi-annual Maternal, Newborn and Child Health Week (MNCHW) | A week program
| Commemoration of World Breastfeeding Week (Symposium, outreach) | Jan Dec | Physical | Enlightening the mothers on the importance of breastfeeding | Reproductive,maternal and neonatal heaith(040301)
| 3 days training of 177 health workers acoss the 3 senatorial districts on Maternal, Infant and Young Child Nutrition (MIYCN) | Jan Dec | Physical |  | Nutrition (040306)
| Conduct of 2 rounds of supportive supervision on effective growth monitoring, promotion and nutrition services in 177 wards across the 16 LGAS | Jan Dec | Physical |  | Nutrition (040306)
| Food demonstration activities across 177 health facilities in Ekiti State | Jan Dec | Physical |  | Nutrition (040306)
| 2 days training of 177 health workers acoss the 3 senatorial districts on Integrated Management of Acute Malnutrition (IMAM) | Jan Dec | Physical |  | Nutrition (040306)
| Active case search of malnourished children across 16 LGAs in Ekiti State | physical | monitoring and evaluation | Number of cases of malnurished children generated | Nutrition (040306)
| Nutrition Project: purchase of health and medical equipment | physical | Vendor | Generating health and medical equipment. | Funtional health facilities(040501)
TB
12 | Conduct sensitisation training on Leprosy and Buruli Ulcer for Medical students/ Nursing school/ college of health Technology. Targeting 300 participants | Jan - Dec | Visit to selected school to carry out the sensitisation training. | No of school visited and No of Student trained | community Interventions (040201) |  | At least 1 medical school,1 school of Nursing School and I college of health Technology school | sensitisation Training conducted | Increase knowledge of Medical /Nursing and Health Tech student on Leprosy and BU case finding. | 800000
13 | Conduct 3 days National TB testing week | Jan, May | outreaches activities in designated sites and awareness creation on Leprosy and BU | No of outreaches conducted and sensitisation campaign carried out and No of health facilities that has access to IEC materials | community Interventions (040201) |  | At least 3 Outreaches per LGA and world Leprosy conducted | Childhood TB testing week conducted and world Leprosy conducted | Increase Childhood TB and Leprosy case detection and access to quality treatment services | 4000000
| Produce and distribute IEC materials on TB and Leprosy |  | IEC production and Distribution | No of health facilities that has access to IEC materials | Planned Preventive Maintenance (040502) |  | 100% of Health care facilities both private and Public | availability of IEC materials in HF | increase awareness to TB and Leprosy | 3000000
14 | conduct Quaterly TB outreach ( 1 per LGA in a quarter )utilizing portable disgital x-rays and rapid molecular testing platforms | Quarterly | supportive supervision to desgnated DOTS sites by State Team Members | No of supportive supervision conducted | community Interventions (040201) |  | At least 15 supportive supervision to at least 6 LGA per quarter | supervision to HF conducted | improved health care workers performance | 700000
| One days capacity building for 100 frontline health workers ( in Two batches of 50 per batch) working at selected DOTS clinics from all levels of Health facilities in both public and private sectors on implementation and scale up of TPT utilisation | Weekly |  |  | Community structures(040202)
| On the job mentoring of DOTS Staff by 5 State team member during quarterly suportive supervision to DOTS facilities at least 5 facility in 5 LGA per quarter to ensure completesness of TPT and proper documentation Refreshment allowance shall be provided for DOTS staff and DSA for State team |  |  |  | Integrated Supportive Supervision (040104)
| Provision of Transport support to trace Contact of 500 Index TB case and reversal contact tracing of diagnosed children with TB |  |  |  | Planned Preventive Maintenance (040502)
| conduct 3 days National Childhood TB week |  |  |  | Communicable diseases(040304)
| commenmoration of World TB day |  |  |  | community Interventions (040201)
| One day Capacity Building of 100 DOTS staff on Adherence Counselling |  |  |  | Effective governance of the health system(0401)
| Establish defaulter tracking system across 16 LGA with provision of communication ( 2000) /Transportation allowance ( 5000)for DOTS Staff on no of loss to follow up patients tracked and bring back to treatment ( Target 5 % of total case registered annualy) |  |  |  | Planned preventive Maintenance(040502)
| Establishaditinal two DRTB OPD clinics in 2 LGA to complement 5 existing one. |  |  |  | Functional Health Facilities(040501)
HIV
15 | Testing and Sensitization on HIV in higher Institutions in the State | Bi-monthly | Conduct an outreach to selected Higher Institution | Number of individuals tested for HIV | community Interventions (040201) | 5000000 | Students; Adolescents and Young People | Number of this age group who counselled, tested and received result | Increased awarenes of HIV among the adolescent and young population | 800000
| Procurement of HIV Test kit | Bi- Annual | Procurement of HIV Test Kit | Quantity of test kits purchased | Planned Preventive Maintenance (040502) |  | Students; Adolescents and Young People | Quantity of test kits purchased | Availability of test kit for use | 5000000
| Commemmoration of World Hepatitis Day | July,2025 | 1. Rally/ Sensitization/ Mobile outreach/ Testing in the 16 LGAs | Number of individuals tested for HBV & HCV | community Interventions (040201) |  | General Population | Number of individuals who know their status | Increased awarenes of HBV & HCV in the 16 LGAs | 3000000
Hold Bimonthly State/LGA data review meeting
| Conduct Bi-monthly Data Quality Assurance to Comprehensive and Spokes Sites to ensure quality of data generated and reported on NDARS (National Data Reporting System) | Monthly |  |  | Integrated National Disease Surveillance(040801)
| Conduct 2 days quarterly targetted outreaches to 5 communities with low rate of HIV testing and treatment gap | Quarterly | To promote HIV testing and treatment gap. |  | Routine Information System(040701)
| Conduct quarterly Joint Supportive Supervision to the comprehensive sites to improve service delivery | Jan Dec |  |  | Monitoring and Evaluation (040704)
BHCPF
16 | Conduct a 5 day quarterly Intergrated Supportive Supervision to BHCPF Health Facilities by 40 BHCPF State team members. | Quarterly | To promote on the job training through regular ISS to focal PHCs. | % of PHCs that the state visited for ISS | Integrated Supportive Supervision (040104) | 4500000 | 100% | Integrated Supportive supervision to 177 BHCPF facilities | Quality service delivery | 7000000
| Conduct a day monthly BHCPF mentoring visits to 177 eligible PHC s by 80 mentors, monitored by 5 state core team members | Monthly | To support BHCPF HFs in development, review and implementation of their business and quality improvement plans | % of PHCs visited by a mentor | Monitoring and evaluation (040704) |  | 100% | To conduct monthly viisit to to BHCPF facilities | Quality service delivery | 6000000
| Conduct bi-annual one day non-residential BHCPF gateway Stakeholders meeting on the implementation status for 45 person | Quarter 2 &4 | To examine and review progress and challenges in BHCPF implementation towards achieving program objectives. | no of BHCPF gateway meeting done with minutes of meetings | Health sector coordination mechanisms (040103) |  | 100% | To examine and review progress and challenges in BHCPF implementation towards achieving program objectives. | Ensure quality service delivery | 800000
NTD
17 | Mass administration of medicines for Onchocerciasis, schistosomiasis and soil transmitted helminths | February, Aug, Nov. | distribution of ivermectin and praziquantel and mebendazole tablets to children 5-14 year accross all eligible persons | Percentage coverage | Community Interventions (040201) |  | 80% treatment coverage | all eligible population treated with ivermectin | reduction in morbidity | 50000000
| Mass administration of medicines for schistosomiasis and soil transmitted helminths | Third Quarter | distribution of praziquantel and mebendazole tablets to children 5-14 years | Percentage coverage | Community Interventions (040201) |  | 80% treatment coverage | all eligible treated with mebendazole | reduction in morbidity | 30000000
| Conduct 2 days skin camp in collaboration with NTD in 8 LGA with report of Leprosy and BU | Weekly |  |  | Communicable diseases(040304)
| Constitute and conduct quarterly AIDs, TBL, Malaria & NTDs (ATM-NTDs) technical working group (TWG) meeting | Quarterly |  |  | Communicable diseases(040304)
| Conduct 2024 review and 2025 state level planning meeting of NTDS activities among 16 State NTDs Officers and 32 LGA - NTDs Officers | Jan Dec |  |  | In service traininig (continuing education)(040403)
| Conduct 2025 world NTDs day celebration in Ekiti State with the attendance of 100 stakeholders | Yearly |  |  | Integrated supportive supervision(040104)
| Conduct training of 32 state and 32 LGA officers on mass administration of medicines for onchocerciasis, Schistosomiasis and soil transmitted helminthes | Jan Dec |  |  | Health sector coordination mechanisms(040103)
| Conduct training of 900 FLHWs and 8500 CDDs and supervision of mass administration of medicines for onchocerciasis, schistosomuiasis and soil transmitted helminmthes | Jan Dec | Vendor |  | Integrated supportive supervision(040104)
| To conduct epidemiological assessment for schistosomiasis and Soil Transmkitted Helminthes among school aged children with 30 stool and urine samples collected per ward | Jan Dec | Vendor |  | Monitoring and Evaluation (040704)
| carry out morbidity management and disability prevention for 50 patients with lymphoedema and hydrocele on quarterly basis | Quarterly |  |  | Research and development(institutional review board,clinical trials)(040703)
Human Resource for Health and Minimum Service Package (HRH&MSP)
| Training of HRH focal person across the 16LGAs level and OICs on the use of current version of NPHCDA PHC-IS Primary Health Care Information System platform | Jan-June | physical training on the use of current version of NPHCDA PHC-IS | strengthening the number of PHC services performance. To also increase patronage in intervention in all health facilities |  |  | 100% 319 Staffing Health Facilities and Timely reporting | to identified the gaps and attrition in PHC health facilities level | Improved health facilities service delivery | 10000000
18 | Capacity Building For Stakeholders on Development of Minimum Service Package according to PHCUOR of National Primary Health Care Across the State | Jan-Dec | Residential training | To strengthening the health service delivery across the PHC facilities level |  | 10000000 | 100% | To develop minimum service packages for service delivery for the PHC in the State. | enhance performance and progress of service delivery in health facilities | 50000000
19 | Bi-annual review meeting of HRH with Stateholder and 16 LGAs Focal to discuss Root Cause Anlysis of HRH | Jan-Oct | physical meeting | To identify the problem and gaps in health workforce. |  |  | number of gaps identified | to know the gaps of health workerforce | enhance optimal performance | 2000000
| Monthly PHC integrated review meeting | Jan Dec | Physical meeting | strengthening PHC integration for optimal service delivery | Health sector coordination mechanisms (040103) |  | at least 100% covarage in interventions | To address identified gaps in all PHC programs | Improved access to services performance | 15000000
20 | Renovation of PHC Facilities across the state | Jan Dec | renovation of facilities for 5 LGA | 100% | functional Health Facilities (040501) | 10000000 | availability of PHC facilites | strenghtening of Health service | improvement of service delivery | 15000000
HEALTH EDUCATION
21 | Purchase of Bluetooth speakers for 177 wards and megaphones batteries | Jan-Dec | purchase of bluetooth for 177 wards | 80% of existing bluetooth | Planned Preventive Maintenance (040502) | 7860093.59 | LGA Hes | Availability of bluetooth | To create awareness aboutPHC services | 20000000
| Production of IEC/BCC/Other material and airing of Radio jingles/PSA on TV/ TV/radio appearnace etc | Jan-Dec | Production of jingles & airing on radio | 100% TV, radio appearance |  |  | Paopulace | To disseminate information on radio | To sensitize the populace about PHC services | 35000000
| One-day Capacity building of 200 HW on Interpersonal communication and counselling to improve quality of care and service delivery. |  |  |  | Evidence generation and utilisation(0407)
| Train 50 FLHWs & 250 CDDs and supervise hygiene promotion activities at the community level |  |  |  | Routine information system(040701)
| One day Advocacy meeting and awareness creation for 100 community leaders/gatekeepers on Implementation and scale up the community approach to improving access to TPT. |  |  |  | Integrated supportive supervision(040104)
TOTAL | [5 empty] | 82860093.59 |  |  |  | 764540000