## Sheet1
EKITI STATE UNIVERSAL BASIC EDUCATION BOARD, ADO – EKITI
WORK PLAN FOR THE STATE BASIC EDUCATION BUDGET
S/N | SUB THEMATIC AREA | OBJECTIVES | OUTCOMES | CORE INDICATORS | TASKS/ INTERVENTIO NS/INITIATIVE | PROGRAMME CLASSIFICATION | GEO-LOCATION CODE | MTEF ENVELOPE | STRATEGY FOR 2025 -2027 | BASELINE DATA 2024/ 2025 ACADEMIC SESSION | KEY DELIVERABLES | YEAR 2025 | YEAR 2026 | YEAR 2027 | BUDGET(In N) | RESPONSIBLE MDA
1 | Digitalization of schools | i. To procure and install necessary devices for digitalization of 5 schools annually. | i. Procurement of routers and laptops for all schools, Table for all teachers, Projectors with screen per class and Wi-Fi in all Basic Education Schools | 5 schools digitized annually | i. Infracstrural support for easy access of schools and pupils information. | 050402 | i. Ado (61320100) ii.Ikere(61331000) iii. Ido (61310800) iv. Ikole (61311100) v. Ekiti West (61320500) | STATE | i. Carry out Needs Assessment and Market Survey. | 3 School digitized. | i. Routers and Laptops and Tablets procured and distributed and installed in 5 Schools annually. | 90,000,000 | 95000000 | 97000000 | 282000000 | SUBEB
|  | ii. To develop Basic Education Website and Portal in all the focus Schools. | iii. Development of Basic Education Website and Portal in all Basic Education Schools. | i. Uploading of learners information/data into schools websites by the teachers on a regular basis in 5 schools annually | ii. Teachers, Learners and Parents/Guardians have access to ICT, schools and learners information. |  |  |  | ii. Follow Due Process. |  | ii. Functional website and Portal in 5 digitized schools | 2,500,000 | 2700000 | 3000000 | 8200000
|  | iii. To develop educational contents appropriate for the learners in the focus schools. | iii. Development of educational contents appropriate for the learners in the focus schools. | iii. Educational contents appropriate for the learners developed in the 5 focus schools annually. | Easy access to educational content | [5 empty] | iii. Educational Software are developed and deloyed into the digitized schools. | 3,000,000 | 3200000 | 3500000 | 9700000
S/N | SUB THEMATIC AREA | OBJECTIVES | OUTCOMES | CORE INDICATORS | TASKS/ INTERVENTIO NS/INITIATIVE | PROGRAMME CLASSIFICATION | GEO-LOCATION CODE | MTEF ENVELOPE | STRATEGY FOR 2025 -2027 | BASELINE DATA 2024/ 2025 ACADEMIC SESSION | KEY DELIVERABLES | YEAR 2025 | YEAR 2026 | YEAR 2027 | BUDGET(In N) | RESPONSIBLE MDA
2 | School safeguard and security | Construction of Perimeter fence with gate house for safety of lifes and properties in schools | Safety of learnings lifes and properties. | 30 Perimeter fence with gate house and security post constucted annually. | Assurance of safety in basic schools | 050501 | 61341700 |  | i. Carry out Needs Assessment and follow due process | 20% of schools have Perimeter Fence. | Perimeter fence with gate house and security post constructed in 120 schools | 452,000,000 | 650000000 | 750000000 | 1852000000 | SUBEB
|  | ii. Recruitment of Day and Night Guards to all Basic Education Schools. | Secured school environment | . Ii. 200 security guards employed and posted to 100 schools | i. Advertisement for Security Guards vacancies in all Basic Education Schools in Ekiti State | 050505 |  |  | i. Carry out Personnel audit and advertise for security guard vacancies in schools | 30% of schools have both day and night guard | ii. Day and Night Guards recruited. | 10,000,000 | 12000000 | 15000000 | 37000000
S/N | SUB THEMATIC AREA | OBJECTIVES | OUTCOMES | CORE INDICATORS | TASKS/ INTERVENTIO NS/INITIATIVE | PROGRAMME CLASSIFICATION | GEO-LOCATION CODE | MTEF ENVELOPE | STRATEGY FOR 2025 -2027 | BASELINE DATA 2024/ 2025 ACADEMIC SESSION | KEY DELIVERABLES | YEAR 2025 | YEAR 2026 | YEAR 2027 | BUDGET(In N) | RESPONSIBLE MDA
3 | Out-of-school-children (OOSC) | i. To ensure all school-age children are enrolled in schools, | Basic education for all school age children | 2% decrease in OOSC annualy | Reduction of OOSC in Ekiti state | 050202 | 61341700 | STATE | i. Production of Bill Boards, Fliers, Hand bills, etc | 819 OOSC re-schooled in 2025 | Increase in School enrolment | 70,000,000 | 77600000 | 81000000 | 228600000
|  | ii. mass literacy in Basic Education | [6 empty] | ii. Production and hearing of Radio Jingles
S/N | SUB THEMATIC AREA | OBJECTIVES | OUTCOMES | CORE INDICATORS | TASKS/ INTERVENTIO NS/INITIATIVE | PROGRAMME CLASSIFICATION | GEO-LOCATION CODE | MTEF ENVELOPE | STRATEGY FOR 2025 -2027 | BASELINE DATA 2024/ 2025 ACADEMIC SESSION | KEY DELIVERABLES | YEAR 2025 | YEAR 2026 | YEAR 2027 | BUDGET(In N) | RESPONSIBLE MDA
4 | Production and use of uniform schemes of work and lesson notes | i. To ensure adequate coverage and standardization in the preparation of uniform schemes of work and lesson notes | i. Uniform schemes of work and lesson notes produced to ensure quality delivery of subject matter. | 6,603 scheme of work and 22,593 lesson notes produced and distributed to schools per session | i. Produce uniform schemes of work and lesson notes for the schools in Ekiti State. | 050402 | 61341700 | STATE | i. Engage Consultant for the production of uniform schemes of work and lesson notes | i. 6.603 scheme of work are currently in use in schools across the state. | i. 6,603 schemes of work procured and distributed to public primary schools | 25,544,700 | 27800000 | 29503000 | 82847700 | SUBEB
|  | ii. To train and retrain Teachers, Education Officers and instructors for effective and efficient instructional delivery |  |  | ii. Evaluate teachers on the use of uniform schemes of work and lesson notes | 050401 |  |  | ii. Produce and distribute uniform schemes of work | ii. initiated preparation of draft schemes of work and lesson notes in selected subjects by selected subject specialist | ii. 22,593 lesson note procured and distributed to primary schools
iii. Partner with relevant stakeholders to follow up on the utilization of the scheme.
|  |  | Teachers, Education Officers and instructors trained to enhance effective and efficient instructional delivery | ii.7,531 Teachers, 70 Education Officers and 20 Instructors trained on instructional delivery | i Train teachers on the use of uniform schemes of work and lesson notes | 050403 |  |  | iii. Train Teachers, Education Officers and instructors on the use of uniform schemes of work and lesson notes. |  | i. 7,531 teachers, 70 education officers and 20 instructors trained on instructional delivery | 304,840,000 | 310400000 | 315520000 | 930760000
S/N | SUB THEMATIC AREA | OBJECTIVES | OUTCOMES | CORE INDICATORS | TASKS/ INTERVENTIO NS/INITIATIVE | PROGRAMME CLASSIFICATION | GEO-LOCATION CODE | MTEF ENVELOPE | STRATEGY FOR 2025 -2027 | BASELINE DATA 2024/ 2025 ACADEMIC SESSION | KEY DELIVERABLES | YEAR 2025 | YEAR 2026 | YEAR 2027 | BUDGET(In N) | RESPONSIBLE MDA
5 | Teachers redistribution in primary schools in Ekiti State; Needs Survey | i. To ensure availability of teachers in all subjects and schools | Improved academic performance in all schools | i. Equitable Pupil / Learner Ratio | i. Identify areas of surpluses and vacancies in teachers’ postings | 050405 | 61341700 |  | i. Identify vacancy areas on subject basis in schools | i. 7,132 teachers and 130,357 students in public secondary, 8,256 teachers and 165,683 publics in primary schools and 168 teachers/instructors and 2,222 students in the GTCs | Appropriate distribution of teachers. | 20,000,000 | 22000000 | 25400000 | 67400000 | SUBEB
|  | ii. To improve retention of teachers in hard-to-staff schools |  | ii. Percentage of reduction in staff vacancy in subject areas | ii. Redistribute available Teachers in the State and equip them for effective teaching and learning | 050405 |  |  | ii. Need-based posting of teachers to be done | ii. 18:1 students/teacher ratio for secondary schools, 20:1 pupils/teacher ratio in public primary and 13:1 students/teacher ratio in technical colleges
|  | iii. To improve academic performance of students in all subject areas across schools |  | iii. Number of teachers trained | iii. Monitor schools to enforce compliance to posting instructions | 050401 |  |  | iii. Enforce deployment policy to increase retention of teachers
|  | iv. To train and retrain teachers to improve their capacity |  |  | iv. Train teachers to improve their productivity | 050403 |  |  | iv. Incentivize teachers deployed to hard-to-staff schools
v. Build or provide accommodation for the teachers deployed to rural areas
vi. Carry out Monitoring of teachers for posting compliance
vii. Train teachers to improve their productivity
|  | To fill vacancies arising from retirement and death | Available vacancies filled | 3997 Teaching and non-teaching staff recruited | Recruitment of teachers | 050405 |  |  | Advertisement, recruitment and posting of newly empolyed teaching and Non-teaching staffs | 7,359 teachers in post as at 2025 | 1,333 teaching and non-teaching staff recruited and posted to schools annually.
S/N | SUB THEMATIC AREA | OBJECTIVES | OUTCOMES | CORE INDICATORS | TASKS/ INTERVENTIO NS/INITIATIVE | PROGRAMME CLASSIFICATION | GEO-LOCATION CODE | MTEF ENVELOPE | STRATEGY FOR 2025 -2027 | BASELINE DATA 2024/ 2025 ACADEMIC SESSION | KEY DELIVERABLES | YEAR 2025 | YEAR 2026 | YEAR 2027 | BUDGET(In N) | RESPONSIBLE MDA
6 | Increase in Schools’ enrolment and safe space in schools | i. To provide safe spaces in schools | i. Increased access to teaching and learning across communities in Ekiti State | i. Number and percentage of schools with safe space facilities | i. Provide facilities to create safe spaces in schools. | 050501 | 61341700 | STATE | i. Establishment of safe guard desk, school safe guard team and grievancies reporting channel. | i. 38 (%) Junior public secondary schools including the 3 special schools and 615 public primary schools were fenced | i. Accurate Record of enrolment, retention, transition and completion made available. | 20,000,000 | 25000000 | 27500000 | 72500000 | SUBEB
[5 empty] | ii. Train personnel to put the facilities to use | 050403
|  | ii. To provide support for girl child learning | ii. Increased enrolment, retention, transition and completion of schools by pupils/ students of primary and secondary schools | ii. Number of girl child supported for Junior Secondary school completion | iii. Provide support for girl child education in the state. | 050305 |  |  | ii. Policy implementation of girl-child education
|  | iii. To provide facilities and resources to support enrolment, retention and completion of special students in schools | iv. To improve on students/pupils enrolment, retention, transition and completion (RTC) | iii. % increase in the pupils/ students enrolment, retention, transition and completion | iv. Provide facilities and resources to support enrolment, retention and completion of special students in schools | 050402
v. Provide facilities for Junior Secondary school completion by disadvantaged /vulnerable students (GBV, teenage pregnancy victims,
[5 empty] | vi. Organize community sensitization and institute education system to address adolescent reproductive etc. | 050202
[5 empty] | vii. Provide positive behavioural interventions such as coaching and mentoring programmes on behavioural management for adolescent. | 050403
S/N | SUB THEMATIC AREA | OBJECTIVES | OUTCOMES | CORE INDICATORS | TASKS/ INTERVENTIO NS/INITIATIVE | PROGRAMME CLASSIFICATION | GEO-LOCATION CODE | MTEF ENVELOPE | STRATEGY FOR 2025 -2027 | BASELINE DATA 2024/ 2025 ACADEMIC SESSION | KEY DELIVERABLES | YEAR 2025 | YEAR 2026 | YEAR 2027 | BUDGET(In N) | RESPONSIBLE MDA
7 | Digital skills in schools | To build capacity of teachers and learners on digital literacy skills and increase the percentage of students graduate with employable skills | Digital training and skills impacted to teachers and students leading to enhanced skills in specific areas such as HDMI, Robotic and Coding etc. across public schools in Ekiiti | Appreciable increase in the number of students and teachers equipped with digital literacy skills | Train teachers and learners on digital skills in specific areas such as HDMI, Robotic and coding skills in public schools | 050403 | 61341700 | STATE | i. Review ICT Curriculum in Basic Education schools to meet contemporary demands. | i. 200 teachers trained on on-line teaching proffessional development | Basic Education school teachers equipped with digital skills | 252,440,000 | 273500000 | 288060000 | 814000000 | SUBEB
[9 empty] | ii Train all schools ICT teachers on basic digital literacy and applications. | ii. 800 teachers trained in digital skills and 420 ICT teachers trained on remote teaching
iii. Organize TOT for teachers on specialized digital skills programme
[9 empty] | iv. Provision of training kits for robotic and coding skills in Ekiti State. |  |  | 75,000,000 | 93750000 | 117187500 | 285937500
v. Incentivize innovations and excellent performance including successful pitching with industry and technical players.
vi. Provide Digital learning infrastructures in all the Basic Education schools in Ekiti State
vii. Provide adequate funding for the training of teachers and learners on digital innovations
S/N | SUB THEMATIC AREA | OBJECTIVES | OUTCOMES | CORE INDICATORS | TASKS/ INTERVENTIO NS/INITIATIVE | PROGRAMME CLASSIFICATION | GEO-LOCATION CODE | MTEF ENVELOPE | STRATEGY FOR 2025 -2027 | BASELINE DATA 2024/ 2025 ACADEMIC SESSION | KEY DELIVERABLES | YEAR 2025 | YEAR 2026 | YEAR 2027 | BUDGET(In N) | RESPONSIBLE MDA
8 | Education Management Information System (EMIS) | i. To build capacity of EMIS/LEMIS Officers on effective data management and analysis | i. EMIS/LEMIS Officers trained on data capturing and management for policy planning and decision making | i. 60 EMIS/LEMIS officers trained on monitoring of data management in schools | Building of EMIS/LEMIS officers capacity on data management. | 050403 | 61341700 | STATE | i. Digitalize the operation of the SUBEB on data management | i. 350 teachers and Education Officers trained on EMIS | i. 60 EMIS Officers trained on data capturing for Annual School Census | 7,200,000 | 8000000 | 10500000 | 25700000 | SUBEB
|  | ii. To train school data officers SDO on data collation and storage at the school level | teachers trained on data capturing and management for policy planning and decision making | 578 school Based data officer trained on effective data collation at school level | Building of school Base Data officers capacity on data management. | 050403 |  |  | ii. Train and retrain of school level EMIS Officers for data collection, collation and management | ii. Annual School Census forms produced for all Basic Education schools in 2024 | ii. All Basic Education schools Registrars, Head teachers and Principals trained on Annual School Census. | 23,120,000 | 25700000 | 31380000 | 80200000
iii. Provide adequate fund for the training of EMIS Officers at the State and school levels
iv. Provide internet facilities/ subscription at the State and at school levels
|  | ii. To produce Annual School Census for comprehensive information on schools and pupils/students | ii. Annual School Census conducted and report produced | v. Conduct of Annual School Census completed | Conduct annual school census | 050603 |  |  | Organize and conduct Annual School Census programme |  | i. Annual School Census forms produced and census conducted. | 32,000,000 | 34500000 | 35700000 | 102200000
ii. Annual School Census Report produced
S/N | SUB THEMATIC AREA | OBJECTIVES | OUTCOMES | CORE INDICATORS | TASKS/ INTERVENTIO NS/INITIATIVE | PROGRAMME CLASSIFICATION | GEO-LOCATION CODE | MTEF ENVELOPE | STRATEGY FOR 2025 -2027 | BASELINE DATA 2024/ 2025 ACADEMIC SESSION | KEY DELIVERABLES | YEAR 2025 | YEAR 2026 | YEAR 2027 | BUDGET(In N) | RESPONSIBLE MDA
9 | Capacity building of School Administrators and teachers on structured pedagogy practice | To build the capacity of the school heads in good quality leadership so as to enhance their productivity | i. Schools’ leadership capacity in Ekiti State built to improve learning outcomes | i. 50 Principals trained annually | Train the leadership of schools to improve their management styles with a view to increase learning outcomes | 050403 | 61341700 | STATE | i. Source for adequate fund for the training of schools' leadership | ii. 50 Principals trained on mentorship and leadership in 2025 | All Principals and Head-teachers received leadership training to improve their productivity | 21,000,000 | 25000000 | 27000000 | 73000000 | SUBEB
|  |  | ii. Enhanced management leadership in schools | ii. 250 Headteachers trained annually |  |  |  |  | ii. Select Principals and Head teachers to be trained on leadership | i. 400 primary school Head teachers trained on leadership in 2025 |  | 105,000,000 | 110000000 | 115000000 | 330000000
|  |  |  | iii Percentage increase in the number of Principals/Head teachers equipped with leadership skills |  |  |  |  | iii. Organise leadership training for School Principals and head teachers
|  | to build the capacity of the teachers on implementation of literacy and numeracy structured pedagogy practice in schools with a view to increase learning outcomes | Improved teachers capacity on implementation of literacy and numeracy structuerd pedagogy practice in schools | 1880 teachers trained annually | Train the teachers to improve their capacity on implementation of literacy and numeracy structured pedagogy practice in schools with a view to increasing learning outcomes |  |  |  | i. Source for adequate fund for the training of schools' leadership | 1250 primary school teachers trained on phonics in 2025 | All Teachers received appropriate training to improve their productivity | 225,600,000 | 250000000 | 270000000 | 745600000 | SUBEB
[9 empty] | ii. Select Principals and Head teachers to be trained on leadership | 813 primary school teacher trained on strenghten Mathematics and Science Education in 2025
iii. Organise leadership training for School Principals and head teachers
S/N | SUB THEMATIC AREA | OBJECTIVES | OUTCOMES | CORE INDICATORS | TASKS/ INTERVENTIO NS/INITIATIVE | PROGRAMME CLASSIFICATION | GEO-LOCATION CODE | MTEF ENVELOPE | STRATEGY FOR 2025 -2027 | BASELINE DATA 2024/ 2025 ACADEMIC SESSION | KEY DELIVERABLES | YEAR 2025 | YEAR 2026 | YEAR 2027 | BUDGET(In N) | RESPONSIBLE MDA
10 | Continuous feeding of the students/ pupils of the 3 Special Schools | To ensure the well-being of the students in the Special Schools | Students/ pupils in Special Schools are well fed | 687 of students /pupils fed | Provide hygienic food for the students /pupils of the Special Schools | 050203 | 61341700 | STATE | i.Regular update of the enrolment of the students/ pupils in the 3 special schools for adequate provision for their feeding | 687 students/pupils of the 3 special schools are availableb to be fed and maintained. | 687 Students and pupils of the 3 special schools are fed | 400,000,000 | 500000000 | 625000000 | 1525000000 | SUBEB
ii. Select good food vendors for the feeding programme
iii. Provide for the feeding of the pupils/ students
S/N | SUB THEMATIC AREA | OBJECTIVES | OUTCOMES | CORE INDICATORS | TASKS/ INTERVENTIO NS/INITIATIVE | PROGRAMME CLASSIFICATION | GEO-LOCATION CODE | MTEF ENVELOPE | STRATEGY FOR 2025 -2027 | BASELINE DATA 2024/ 2025 ACADEMIC SESSION | KEY DELIVERABLES | YEAR 2025 | YEAR 2026 | YEAR 2027 | BUDGET(In N) | RESPONSIBLE MDA
11 | Provision of habitable classrooms for teaching -learning process. | To ensure conducive learning environment in all Basic Education Schools. | All school age learners learn in good environment. | 80 classrooms constructed | Provision of conducive learning environment. | 050501 | 61341700 | STATE | Advertisement, bidding and award of contract | 20% of schools are with conducive learning environment | i. Construction of new classrooms | 1,703,581,231 | 2060000000 | 2375000000 | 6138581231 | SUBEB
|  |  |  | 100 classrooms renovated |  | 050501 |  |  | E-payment/cash transfer |  | ii. Renovation of existing bad classrooms
|  |  |  | 2000 units of Nursery furnitures procured |  | 050502 |  |  |  |  | iii. Fencing of Public Basic education Schools
|  |  |  | 3000 Pupils furniture procured |  | 050502 |  |  |  |  | iv. Construction of sanitary facilities (Toilet, Boreholes, Urinals)
|  |  |  | 120 teachers furniture procured |  | 050502 |  |  |  |  | v. Provision of health Facilities (Sick Bays)
S/N | SUB THEMATIC AREA | OBJECTIVES | OUTCOMES | CORE INDICATORS | TASKS/ INTERVENTIO NS/INITIATIVE | PROGRAMME CLASSIFICATION | GEO-LOCATION CODE | MTEF ENVELOPE | STRATEGY FOR 2025 -2027 | BASELINE DATA 2024/ 2025 ACADEMIC SESSION | KEY DELIVERABLES | YEAR 2025 | YEAR 2026 | YEAR 2027 | BUDGET(In N) | RESPONSIBLE MDA
13 | Procurement of instructional materials | To procure instructional materials on literacy and numeracy in all Basic Education Schools in Ekiti state. | Teachers and learners learn with modern and relevant instructional materials in all Basic Education Schools. | 100% of basic schools have instructional materials to support literacy and numeracy teaching in schools | Follow due processand collate the names of the beneficiary schools | 050402 | 61341700 | STATE | E-paymeny/cash transfer | 35% of basic schools in the state are having their teacing supported with instructional materials | Instructional materials ( marker, pencils, cardboard, flip chart stand and e.t.c) procured and delivered to all schools | 660,000,000 | 680000000 | 710000000 | 2050000000 | SUBEB
|  | Procurement and distribution of textbooks on literacy and numeracy to P1-P3 pupils in the state | Promotion of literacy and numeracy proficiency in basic schoools | 100% of P1-P3 learners have English and Mathematics | Follow due processand collate the names of the beneficiary schools |  |  |  | E-paymeny/cash transfer | 10% of learners of P1-P3 are having both English and Mathematics textbooks. | A mathematics and English textbooks forevery leaner of P1-P3 in the 928 schools | 245,251,700 | 260800000 | 300000000 | 806051700
S/N | SUB THEMATIC AREA | OBJECTIVES | OUTCOMES | CORE INDICATORS | TASKS/ INTERVENTIO NS/INITIATIVE | PROGRAMME CLASSIFICATION | GEO-LOCATION CODE | MTEF ENVELOPE | STRATEGY FOR 2025 -2027 | BASELINE DATA 2024/ 2025 ACADEMIC SESSION | KEY DELIVERABLES | YEAR 2025 | YEAR 2026 | YEAR 2027 | BUDGET(In N) | RESPONSIBLE MDA
| Annual school grant | i. To maintain the infracstrcture and resources of schools. ii. To sustain the quality of teaching and learning | i. schools infracstructure and resources are maintained for continuous quality teaching and learning | 928 schools are paid annual school grant annually | Payment of annual school grant for the the basic school in Ekiti State | 050401 | 61341700 | STATE | E-payment/cash transfer | 928 schools are currently receiving school grant | 928 schools received school grant | 170,781,000 | 171600000 | 175891000 | 518272000 | SUBEB/MOE
| TOTAL | [10 empty] | 4,918,858,631.166 | 5718550000 | 6428141500 | 17065550131.1