## Progress Report
EKITI STATE ACTION ON BUSINESS ENABLING REFORMS (SABER) 2023 BERAP PROGRESS REPORT
Original action plan as published | [9 empty] | Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
1 | Improved transparency in Land Administration and Land-based Investment Process | (i) This reform area will enhance the administration and management of land in Ekiti State; (ii) the reform will also improve trasparency of property registration and unlock capital from this asset class. | A.1. Develop and adopt a long term vision, goals and strategic directions for land and property administration in Ekiti State | Develop a high level strategy document defining a shared vision, measurable goals and strategic direction for land and property administration in Ekiti State | Bureau of Land Services | Office of the Governor, Office of the Secretary to the State Government, Ministry of Finance and Economic Development, Ministry of Justice , Bureau of Lands Service, Ministry of Housing & Urban Development, Ekiti State Internal Revenue Service, Ekiti State Development and Investment Promotion Agency, Ministry of Agriculture and Food Security | N10,004,000.00 | 2023-01-01 | 2023-01-31 | Ongoing Impact/Implication - enhance the administration and management of land in Ekiti State | a. The reconsitution of the Land Administration and Management Project (LAMP) will be completed on or before September 2024. b. The preparation of the high-level strategy is a key deliverable of the LAMP Committee. c. The action step is recaptured under the State's 2024 Business Enabling Reform Action Plan (BERAP) to esure completion. | (i) Reconstitution of Ekiti State's Land Administration and Management Projects Committee. (ii) The Committee will prepare the draft high-level strategy document defining the shared vision, measurable goals and strategic direction for land and property administration in Ekiti State. (iii) The high-level strategy document upon review and approval will be published on the official websites of the state government, Bureau of Land Services and other identified relevant ministries, departments and agencies (MDAs).
|  |  | A.2. Establish and build consesus among relevant MDAs on institutional and policy reforms being proposed and/or implemented including but not limited to developing and maintaining digital titling of all landed properties in Ekiti | Ensure at least 50% of buildings in major towns (Ado, Ikere and Ikole LGAs) are enunerated and recorded | Bureau of Land Services | Office of the Governor, Office of the Secretary to the State Government, Ministry of Finance and Economic Development, Ministry of Justice , Bureau of Lands Service, Ministry of Housing & Urban Development, Ekiti State Internal Revenue Service, Ekiti State Development and Investment Promotion Agency, Ministry of Agriculture and Food Security |  | 2023-01-01 | 2023-06-30 | Done Impact/Implication - The enumeration of the buildings in Ado, Ikere and Ikole Ekiti will contribute significantly to improvement in governance efficiency in resources allocation. | The enumeration and recording of at least 50% of properties in Ado-Ekiti, Ikere-Ekiti, and Ikole Ekiti have been completed. Following the State government's commitment to ensuring efficiency in resource allocation, the action step is recaptured under the State's 2024 Business Enabling Reform Action Plan (BERAP) to ensure the enumeration and recording of all properties in these towns. | To ensure that properties in major towns in the state are enumerated, the following steps are being undertaken - (i) development of an enumeration report on the enumeration exercises carried out in Ado, Ikere and Ikole Ekiti. (ii) Achieve 75% enumeration and recording of properties in the 3 identified towns. (IIi) Procurement - The Office is making some procurements for the continuation of enumeration exercises at these towns in Ekiti State.
|  |  | B.1. Publish the process for obtaining CofO including all relevant MDAs, time frames and costs on the State official website | The Buruea of Land Services in collaboration with Ekiti State Geospatial Centre shall provide comprehensive information on the process of obtaining Certificate of Occupancy in Ekiti State. The user, beneficiairies and recipients of the reform include applicants for land CofO, investors and business owners | Bureau of Land Services | Ekiti State Internal Revenue Services, Ministry of Finance and Economic Development | Not Applicable | 2023-01-01 | 2023-01-31 | Done Impact/Implication: it has enhanced transparency. Citizens and stakeholders in Ekiti State can easily access information about the steps, requirements, and timelines for obtaining CofOs in the state. | Milestones Achieved: a. documentation and publication of the process for obtaining Certificate of Occupancy (CofO) in Ekiti State. b. increase in the number of developers and investors taking on projects within the state contributing to growth in construction and property sectors in the State. The process for obtaining CofOs in Ekiti is published on the link below - https://ekitistate.gov.ng/wp-content/uploads/saber/Process%20for%20obtaining%20CofO%20in%20Ekiti%20State%20.pdf | a. To ensure the sustainability of this reform, the state government recaptured this action in the State's 2024 Business Enabling Reform Action Plan (BERAP) to accommodate any review, update or upgrade b. Continuous stakeholder engagement to promote awareness within the business community of the process for obtaining CofO in the State.
|  |  | B.2. Publish the process for obtaining construction permit including all relevant MDAs, time frames and costs on the State official website | The Ministry of Housing and Urban Development shall provide comprehensive information on the process of obtaining Constrution permits in Ekiti State. The user, beneficiairies and recipients of the reform include applicants for construction permit, investors and business owners | Ministry of Housing and Urban Development | Ekiti State Internal Revenue Services, Ministry of Finance and Economic Development | Not Applicable | 2023-01-01 | 2023-01-31 | Done Impact/Implication: easy access to information about the regulatory process for construction permit from anywhere at any time, reducing the need for physical visits or requests. | Milestone achievement; it has encouraged more people to request for contruction permit; Challenges: encoutering some technical hitches in the payment gateway for the payment of stamp duty The process for obtaining construction permits in Ekiti is published on the link below - https://www.ekitistate.gov.ng/wp-content/uploads/saber/APPLICATION%20PROCESS%20AND%20GUIDELINES%20FOR%20OBTAINING%20BUILDING%20PERMIT%20IN%20EKITI%20STATE.pdf; | (i) The responsible ministry shall contact and collaborate with the Service provider to expedite quick action to remove the hitch (ii) The action step shall be included in the 2024 BERAP in view of any review, update or upgrade
|  |  | B.3. Develop the Terms of Reference (ToR) for creation of data-centric digital archive of CofOs with serchable indexes with a searchable index in accrodance with international standards | The Bureau of Land Services in collaboration with the Ekiti State Geographical Informatoon System project will ensure end-to-end processing of land transactions at the data center and digital archiving of the electronically signed registered CofOs and other instruments | Bureau of Land Services | Ministry of Housing and Urban Development, Office of the Surveyor General and Ministry of Finance | Not Applicable | 2023-01-01 | 2023-06-30 | Done Impact - i. digitized and simplified end-to-end processing of land transactions at the data center. ii. digital archiving of the electronically signed registered CofOs and other land instruments iii. reduce ambiguity and miscommunication as the creation of data-centric digital archive of CofOs; | i. The Terms of Reference for the creation of a data-centric digital archive of CofOs with searchable indexes was developed. ii. The TOR provides a clear structure for the project implementation | Commence the indexation and digitization of existing CofOs in a digital archive.
|  |  | B.4. Digitization and indexation of existing CofOs in a digital archive | Ensure at least 75% of existing certificates are digitzed and archived. | Bureau of Land Services | Ministry of Finance and Economic Development | N125,000,000.00 | 2023-01-01 | 2023-06-30 | Not Started Impact - i. Easy access to the CofOs online, reducing the need for physical storage ii. Eliminating the need for business owners to go to physical offices to get these documents, thereby saving business cost and time. iii. improve operational efficiency and save time compared to manually searching through paper records. | Challenges - Funding for the project | (i) Conduct a comprehensive inventory of all existing CofOs and related documents to determine the scope of digitization; (ii) Infrastructure and Technology Setup (iii) prepare all the required documentation to access funding for the project
|  |  | C. Establishment the Framework for Responsible and Inclusive Land Intensive Agriculture (FRILIA) | (i) Set-up FRILIA Steering Committee to develop FRILIA document to address challenges in Land administration for Agricultural and Industrial purposes in the State; (ii) create a Multistakeholders platfrom (MSP) for consultation on key issues | Ministry of Agriculture and Food security | Bureau of Land Services, Office of Surveyor-General, Ministry of Finance, Agriculture Development Project, Farm Settlement, Ministry of Industry, Trade & Investment,Ekiti State Development and Investment Promotion Agency, Ekiti State Internal Revenue Service, Ministry of Justice | N40,000,000.00 | 2023-01-25 | 2023-06-30 | Ongoing Impact - The adoption of a Framework for Responsible Investment in Land-Intensive Agriculture (FRILA) can lead to positive impacts on environmental sustainability, social equity, economic development, governance, risk management, and stakeholder collaboration. | Milestones - i. Executive Order on the establishment, adoption and implementation of FRILIA has been issued to relevant Ministries, Departments, and Agencies (MDAs). ii Inauguration of the Steering Committee on FRILIA; iii. Inauguration of the Technical Committee on FRILIA. Challenge - The time constraint was the major challenge that led to the delay in the full adoption of the Executive Order in 2023. | Development of the Toolkits/Guidelines for FRILIA;
|  |  | C.1. Issuaance of Executive Order on FRILIA | The Steering Committee shall develop an Executive Order on FRILIA for review by the Ministry of Justice, before execution by the Governor. | Ministry of Agriculture and Food security | Bureau of Land Services, Ministry of Justice, | N5,000,000.00 | 2023-07-03 | 2023-07-31 | Done Impact - It outlines guidelines, principles, and standards that investors and stakeholders must adhere to, ensuring consistency in practices across different regions or sectors. | Milestones (i) The EO established a clear legal and regulatory framework for the adoption and implementation of FRILIA in Ekiti State (ii) the issuance of the EO by the office of the Head of Service. Challenges: Despite its potential benefits, implementing an EO on FRILA may face challenges such as resource constraints, and varying capacities across different regions or jurisdictions. The Executive Order on FRILIA is published on the link below - https://ekitistate.gov.ng/wp-content/uploads/saber/Executive%20Order%20on%20FRILIA.pdf | Create more awareness about the Executive Order on FRILIA
|  |  | C.2. Adoption and implementation of the FRILIA | FRILIA Steering Committee shall ensure the adoption and implementation of FRILIA in the State | Ministry of Agriculture and Food security | Bureau of Land Services, Office of Surveyor-General, Ministry of Finance, African Development Project, Farm Settlement, Ministry of Industry, Trade & Investment, Ekiti State Development and Investment Promotion Agency, Committee on Agriculture in the State House of Assembly | N5,000,000.00 | 2023-08-01 | 2023-08-31 | Not Started Impact - Effective land administration facilitates better urban planning by ensuring that land is allocated and used efficiently for residential, commercial, industrial, and public purposes. This helps in mitigating urban sprawl and promoting sustainable development practices. Transparency in property registration systems can lead to a more efficient, fair, and economically vibrant environment for real estate markets and broader societal development | Challenge - The action was not achieved due to time constraint | (i) Attend the trainings and workshops on FRILIA (ii) development of a work plan on the development of guidelines on FRILIA (iii) the action step is recaptured in the 2024 State Business Enabling Reform Action Plan (BERAP) to ensure adoption and completion.
2 | Improved infrastructure for enhacement of business-enabling environment (regulatory framework for private investment in fibre optic infrastructure) | To build a strong foundation for digital economy through enhaced fast, relaible and accessible fixed broadband to incentivised opertaors for the deployment of fixed broadband in the State. | A. Amendment of the existing legislation/regulations or passing of new legislation/regulation to adopt aggregate fees charged for broadband deployment on a per liner meter basis at a maximum of NGN145 per meter | Upgrade the existing Executive Order on broadband fees to a Law duly passed by the State House of Assembly | Ministry of Housing and Urban Development | Ekiti State Internal Revenue Service, Ministry of Finance, Ekiti State Development and Investment Promotion Agency, Ministry of Infrastructure and Public Utility, and Ministry of Justice | Not Applicable | 2023-01-01 | 31-June-2023 | Done Impact - stimulate economic growth by attracting investment and fostering a conducive environment for business development in the State | Milestones - a. Introduced a strong legal and administrative framework for the adoption of aggregate fees charged for broadband deployment at a maximum of N145/meter by developing the Ekiti State Right of Way Regulations b. Published the Regulations on the state's official website. Available on the link below - (https://www.ekitistate.gov.ng/wp-content/uploads/saber/1.%20Ekiti%20State%20Right%20of%20Way%20Regulations,%202023.pdf) | Create more awareness about the Regulation through various channels - a. official state government social media handles b. Radio & TV Advertisements c. Sensitization Sessions with organised private sector and the business community in the state. d. state government's official website.
|  |  | A.1. maintenace of the aggregate per linear meter fees for broadband deployment | Ensure a law that caps the Right of Way tariff at not more than N145 per linear meter is enacted. | Ministry of Infrastructure and Public Utility | Ministry of Infrastructure and Public Utilities, Ministry of Housing and Urban Development | Not Applicable | 2023-03-31 | 2023-04-28 |  | Milestone - a. The Executive Order on Broadband fees was used to make the Regulation to adopt aggregate fees of N145/m. b. increase in private sector investment in broadband infrastructure as a direct result of reduced fees, leading to expanded coverage and improved service quality | Public Awareness: Publicizing the benefits of reduced fees to raise awareness among consumers, businesses, and policymakers about the positive impacts on economic development, education, healthcare, and overall quality of life. The awareness will be driven through various channels - social media, website, radio & TV advertisements, etc.
|  |  | B. publication of Right of Way (ROW) process | Publish the ROW process on the State website | Ministry of Housing and Urban Development | Bureau of Information and Communication Technology, Ministry of Housing and Urban Development, Ministry of Infrastructure and Public Utility | Not Applicable | 2023-01-01 | 31-June-2023 | Done Impact - Reliable broadband supports e-government initiatives, digital public services, and online civic engagement platforms. It enhances transparency and efficiency in the regulatory process for obtaining the right of way in Ekiti State. | Milestone - a. increase in private sector investment in broadband infrastructure as a direct result of reduced fees, leading to expanded coverage and improved service quality b. Published the Right of Way application process on the state's official website. Available on the link below - (https://www.ekitistate.gov.ng/wp-content/uploads/saber/Right%20of%20Way%20Application%20Process%20in%20Ekiti%20State.pdf) | (i) inclusion of the action step in the 2024 State Business Enabling Reform Action Plan (BERAP) in view of any review, update or upgrade;
|  |  | B.1 Establishment of framework for the ROW process in the State | Establish a framework for ROW deployment across the State | Ministry of Housing and Urban Development | Ministry of Infrastructure and Public Utilities | Not Applicable | 2023-01-01 | 31-June-2023 |  | Milestone - a. A framework for right of way deployment in Ekiti State was developed. b. Increase in private sector investment in broadband infrastructure as a direct result of reduced fees, leading to expanded coverage and improved service quality | Inclusion of the action step in the 2024 State Business Enabling Reform Action Plan (BERAP) given any review, update, or upgrade;
|  |  | B.2. Publish on the state official website, the process for obtaining ROW including all relevant MDAs, timeframes, and costs | Publish all ROW related processes and fees on the State website. | Ministry of Housing and Urban Development | Bureau of Information and Communication Technology, Ekiti State Development and Investment Promotion Agency, Ministry of Infrastructure and Public Utilities | Not Applicable | 2023-01-01 | 31-June-2023 | Done Impact - Improved broadband infrastructure facilitates faster data transfer speeds and more reliable connections. This fosters innovation and entrepreneurship as businesses can leverage high-speed internet for research, development, and launching new digital services. | Milestone - a. increase in private sector investment in broadband infrastructure as a direct result of reduced fees, leading to expanded coverage and improved service quality b. Published the Right of Way application process, including all timelines, relevant MDAs and cost, on the state's official website. Available on the link below - (https://www.ekitistate.gov.ng/wp-content/uploads/saber/Right%20of%20Way%20Application%20Process%20in%20Ekiti%20State.pdf) | Inclusion of the action step in the 2024 State Business Enabling Reform Action Plan (BERAP) given any review, update, or upgrade;
|  |  | C. deployment of non-Gigabit Passive Optical Network (GPON) fibre optic cable kilometres | Ensure deployment of GPON fibre infrastructure across Ekiti State in at least 2,000km across the State. | Ministry of Infrastructure and Public Utilities | Ministry of Housing and Urban Development, Office of the surveyor General and Ministry of Finance, Bureau of Information, Communication and Technology | Not Applicable | 2023-01-01 | 2023-06-30 | Not Started Impact - Improved broadband infrastructure facilitates faster data transfer speeds and more reliable connections. This fosters innovation and entrepreneurship as businesses can leverage high-speed internet for research, development, and launching new digital services. | Challenge - Time constraints | inclusion of the action step in the 2024 State Business Enabling Reform Action Plan (BERAP) as "engage qualified service providers for the deployment of non-Gigabit Passive Optical Network (GPON) fibre optic cable kilometers"
|  |  | C.1 increase in total deployed GPON fibre optic cable kilometres against 2022 baseline meets target. Basic target: 20-99% Stretch target: ˃100% | The State shall ensure that ther is an increase of more that 100% in the total deployed GPON fibre optic cable kilometers against 2022 as baseline | Ministry of Infrastructure and Public Utilites | Ekiti State Development and Investment Promotion Agemcy, Ministry of Housing and Bureua of Lands | Not Applicable | 2023-01-01 | 2023-12-31 |  | Challenge - damages in existing fibre optic and the repair is yet to be done | inclusion of the action step in the 2024 State Business Enabling Reform Action Plan (BERAP) as "increase in total deployed GPON fibre optic cable kilometers against 2022"
3 | Sustainable Large-Scale Investments | (i) to have an effective State invetsment promotion agency for service delivery to investors and targeted efforts towards attracting and retaining investment (ii) to ensure transparency and easier access to information and participation for stimulation of investment in the economy of the State; (iii) to establish effective Public-Private Partnership (PPP) models in the State | A. mandate Ekiti Development and Investment Promotion Agency (EKDIPA) (state-level technical unit/agency) as the lead organization to facilitate PPP and promote investment into the State | Enact a Law establishing a State Investment Promotion Agency and develop a strategic plan to operationalise the agency. | Ekiti State Development and Investment Promotion Agency (EKDIPA) | Ministry of Industry, Trade and Investment, and the Ministry of Justice | Not Applicable | 2023-01-01 | 2023-01-31 | Done Impact - increased investors' confidence with the provision of clear information, streamlined processes, and reliable support throughout the investment lifecycle. This can reduce uncertainty and perceived risks associated with investing in the State. | Milestone - Enactment of legislation officially establishing the Ekiti Development and Investment Promotion Agency (EKDIPA) with clear responsibilities and authority to promote PPPs and attract investment into the state. The law is the Ekiti State Development and Investment Promotion Agency Law (EKDIPA) 2019. The link to the law is - https://www.ekitistate.gov.ng/wp-content/uploads/saber/EKDIPA%20Law%2008%20of%202019.pdf Challenge- lack of understanding of the mandate by some implementing MDAs | Create more awareness among Ministries, Departments, and Agencies in Ekiti State about the mandate of EKDIPA as the lead organization to facilitate PPP and promote investment into the State.
|  |  | A.1. obtain the approval of the State Executive Council (EXCO) mandating EKDIPA as lead agency to facilatate PPP and promote investment into Ekiti State | Enact and implement a State Public Private Partnership Law designatingEKDIPA as lead agency for PPP facilitation | Ekiti State Development and Investment Promotion Agency | Ministry of Industry, Trade and Investment, Ministry of Justice and Ekiti State House of Assembly | Not Applicable | 2023-01-01 | 2023-01-31 | Done Impact - Increased inflows of foreign direct investment (FDI) and domestic investments, driving economic growth and development. | Milestone - a. Approval of the State's EXCO b. Enactment of the Ekiti State Public Private Partnerships (Re-Enactment) Law. c. The link to the PPP Law is - https://www.hoa.ekitistate.gov.ng/dashboard/doc/No.%2010%20of%202020%20-%20EKITI%20STATE%20PUBLIC%20PRIVATE%20PARTNERSHIP%20(re-enactment)%20Bill.pdf | Not Applicable
|  |  | A.2 obtain the approval of HoA mandating EKDIPA as lead agency to facilitate PPP and promote investment into Ekiti State | Enact and implement a State Public Private Partnership Law designatingEKDIPA as lead agency for PPP facilitation | Ekiti State Development and Investment Promotion Agency | Ministry of Industry, Trade and Investment, Ministry of Justice and Ekiti State House of Assembly | Not Applicable | 2023-01-01 | 2023-01-31
|  |  | A.3. implementation of the mandate that EKDIPA should be the lead agency to facilitate PPP in Ekiti State | Enact and implement a State Public Private Partnership Law designatingEKDIPA as lead agency for PPP facilitation | Ekiti State Development and Investment Promotion Agency | Ministry of Justice, Ministry of Agriculture and Food Security, Bureau of Land Services, Ministry of Infrastructure and Public Utilities, Ministry of Industry, Trade and Investment. | Not Applicable | 2023-01-01 | 2023-01-31 | Done Impact - Investments attracted through effective IPAs create jobs and stimulate economic activity in the region. This includes direct employment in new ventures as well as indirect benefits to local suppliers and service providers. | Milestone - Establishment of streamlined processes and guidelines for facilitating PPP projects, including project identification, feasibility assessment, procurement procedures, and contract negotiation. Challenge - Some MDAs do not liaise with EKDIPA in PPP arrangements and facilitations | Circular to be issued to relevant MDAs to liaise with EKDIPA on the PPP facilitation and arrangement Hold collaborative sensitization sessions with relevant MDAs on the role of EKDIPA in the PPP process.
|  |  | B. Establishment of effective PPP models | Develop and agree frameworks to determine the PPP models required for various investment opportunities in the State. | Ekiti State Development and Investment Promotion Agency | Ministry of Industry, Trade and Investment, and the Ministry of Justice | N50,000,000.00 | 2023-01-01 | 31-June-2023 | Not Started Impact - accelerated infrastructure development, as private sector expertise and funding can complement public sector resources. This includes projects such as roads, bridges, airports, ports, and utilities. The state benefits from improved infrastructure without solely relying on public funds, thereby addressing infrastructure gaps more efficiently; | Challenge- a. Time constraint b. lack of technical resources to commence the process | (i) include in EKDIPA's work plan for 2024 (ii) Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | B.1 establishment of Ekiti State Fiscal Commitment and Contigent Liability (FCCL) Management Framework | Develop and obtain State EXCO approval for a Fiscal Commitment and Contigency Liability Management Framework | Ministry of Finance and Economic Development | Ministry of Budget and Economic Planning, EKDIPA | N2,500,000.00 | 2023-01-01 | 2023-03-31 | Not Started Impact - PPPs distribute risks between the public and private sectors more effectively. Private partners often assume certain risks associated with project implementation and operation, such as construction delays, cost overruns, and revenue generation. This mitigates financial burdens on the state and improves project delivery timelines. |  | Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | B.2 establishment of PPP legal and institutional framework, inluding guidelines and manual | EKDIPA to develop guidelines and manual of PPP framework. The beneficiaries are the investors and business owners. | Ekiti State Development and Investment Promotion Agency | Ministry of Trade and Industry | N1,000,000,00 | 2023-01-01 | 31-June-2023 |  |  | recruitment of consultant for the development of framework to be included in EKDIPA workplan for year 2024 Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | B.3 establishment of the PPP disclosure Framework | PPP framework established and published on EKDIPA website | Ekiti State Development and Investment Promotion Agency | Ministry of Trade and Industry | N1,000,000,00 | 2023-01-01 | 2023-06-30 | Not Started Impact - It will provide a clear framework for PPP arrangement in the State PPPs encourage long-term investments in infrastructure and services, as private partners often have a stake in the project's success over its lifecycle (which can span decades). This focus on sustainability ensures that infrastructure assets are well-maintained and continue to benefit the state and its residents for years to come. |  | recruitment of consultant for the development of PPP Disclosure framework to be included in EKDIPA workplan for year 2024 Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | B.4 online publication of the (i) PPP Fiscal Commitment and Contigent Liability (FCCL) Management Framework; and (ii) PPP legal and institutional framework, including guidelines and manual; and (iii) PPP disclosure framework | (i) Amendment of Ekiti PPP Law to include FCCL Management framework (ii) PPP Guidelines and manual to be developed (III) PPP disclosure frameworkto be implemented | Ekiti State Development and Investment Promotion Agency | Ministry of Justice | Not Applicable | 2023-01-01 | 2023-06-30 | Not Started Impact - the frameworks provide clear guildelines and structure for PPP arrangement in the State. it will boost the confidence of private partners | Challenge - non-availability of technical resources, such as the Fiscal Commitment and Contingent Liability (FCCL) Management Framework, to commence the process. | Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion. ensure the development of the PPP Fiscal Commitment and Contingent Liability (FCCL) Management Framework; and (ii) PPP legal and institutional framework, including guidelines and manual; and (iii) PPP disclosure framework
|  |  | B.5. adoption and disclosure of PPP pipeline by EKDIPA (of which at least 50% is linked to climate adaptation and mitigation | Publish a list of PPP projects and their respective status to promote transparency. | Ekiti State Development and Investment Promotion Agency | Ministry of Industry, Trade and Investment | Not Applicable | 2023-01-01 | 2023-12-31 | Done Impact - it will assist in determining the impact of the PPP pipeline projects on the climate emissions in Ekiti State promote transparency of ongoing PPP projects in the state. | The disclosure of the PPP pipeline revealed most of the PPP projects will contribute positively to the State's climate adaptation and mitigation plan. Challenge - lack of adequate technical knowledge | Not Applicable
|  |  | B.6. online publication (or web-based disclosure portal) of the pipeline projects | EKDIPA to publish pipeline projects on her website. The beneficiaries are the potential investors, investors and business owners | Ekiti State Development and Investment Promotion Agency | Bureau of Information and Communication Technology | Not Applicable | 2023-01-01 | 2023-06-30 | Done Impact - PPPs can catalyze development in specific sectors where private sector involvement is critical, such as healthcare, education, renewable energy, and transportation. By leveraging private sector expertise and resources, the state can address sector-specific challenges more effectively. | EKDIPA has published all PPP pipeline projects within the state on its official website. Challenges - lack of adequate technical knowledge (https://www.ekitistate.gov.ng/wp-content/uploads/saber/PUBLIC%20PRIVATE%20PARTNERSHIP%20PROJECTS%20IN%20EKITI%20STATEv2.xlsx) | Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | C. establishment of State Project Facilitation Fund with a minimum funding of 3% of the total pipeline estimated capital investment | Establisha State Wealth Fund which will include Project Facilitation Fund to catalyze private investments | Ministry of Finance and Economic Development | Ekiti State Development and Investment Promotion Agency, Ministry of Budget ,and Economic Planning, Ministry of Justice, and Ministry of Industry, Trade and Investment | N500,000,000 | 2023-01-01 | 2023-06-30 | Done Impact - The State Project Facilitation Fund (SPFF) plays a vital role in catalyzing project development and investment in the state. By securing a dedicated funding source, it promotes economic growth, facilitates infrastructure development, and enhances the overall investment climate. | Ekiti State government has established the State Wealth Fund which includes the project facilitation fund. By securing 3% of the total investment, the fund can provide crucial initial financing that enhances project viability and encourages private investment. | Not Applicable
|  |  | D. develop/update an inventory/database of all investment incetives (Federal and State) available in Ekiti State | Inventory of all investment incentives in the State already developed and published on EKDIPA website. The beneficiaries are the investors and bussiness owners. | Ekiti State Development and Investment Promotion Agency | Ministry of Industry, Trade and Investment | Not Applicable | 2023-01-01 | 2023-01-31 | Done Impact - Transparency: An inventory provides clear information about available incentives, making it easier for businesses to choose Ekiti State as their preferred investment destination. | Developed and published the incentives inventory on EKDIPA's website for easy access. The incentives inventory is in the link below - https://ekdipa.com.ng/ekdipa-api/sites/default/files/2023-12/Inventory%20of%20all%20Investment%20Incentives.xlsx Successfully attracted additional private investment, demonstrating a strong public-private partnership model. Challenge - delay in response from the Federal Agencies such as FIRS | Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | D.1. online publication of the inventory all investment incentives available in the State | Inventory of all investment incentives in the State already published on EKDIPA website. The beneficiaries are the investors and bussiness owners. | Ekiti State Development and Investment Promotion Agency | Bureau of Information and Communication Technology | Not Applicable | 2023-01-01 | 2023-01-31
|  |  | E. Update of EKDIPA website with required information (including information on access to credit) | EKDIPA website to be updated with required information. The beneficiaries are the investors, business owners and potential investors | Ekiti State Development and Investment Promotion Agency | Bureau of Information and Communication Technology | N10,000,000.00 | 2023-01-01 | 2023-06-30 | Done Impact - makes it easier for business owners and investors to find information quickly. | updating EKDIPA's website has led to improved user experience, increased engagement, better performance, and a stronger brand presence, ultimately driving investment in the State | Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | F. organization of quaterly information sessions annually for investors by EKDIPA | Ensure at least 2 sessions are held in 2023 to engage with investors operating in Ekiti State, to discuss among others Business Environment Reforms and tax compliance. | Ekiti State Development and Investment Promotion Agency | Ministry of Industry, Trade and Investment. And Ekiti State Internal Revenue Service | N5,000,000.00 | 2023-01-01 | 2023-12-31 | Not Started Impact - organizing information sessions for investors can significantly enhance engagement, attract new investments, promote economic growth, and foster strong relationships within the investment community | Challenge - Time constraints | Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | G. development and adoption of aftercare and retention program | Develop and implement an aftercare programme that caters to existing investors. | Ekiti State Development and Investment Promotion Agency | Ministry of Industry, Trade and Investment | N1,500,000.00 | 2023-01-01 | 2023-01-31 | Not Started Impact - The development and adoption of aftercare and retention programs can significantly enhance customer loyalty, satisfaction, and overall brand reputation, ultimately leading to increased revenue and business growth. | There was no aftercare and retention programme developed or implemented in 2023. The state government is aware that private sector partners are incentivized to maintain high service quality to meet contractual obligations and protect their reputation, leading to better services for citizens. Further to this, the need to implement this programme will be prioritized in 2024. Challenge - no budgetary provision in 2023 budget | (i) Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion. (ii) Include the action step in EKDIPA's work plan for 2024 (iii) develop an aftercare and retention programme to support investors in 2024.
4 | Increased Transparency of official fees and procedures | (i) This reform area will increase transparency of official fees and procedures focusing on key business environment enabling MDAs in Ekiti State; (ii) the reform will give easier access to regular information for greater regulatory efficiency, lower compliance costs and better regulatory quality; (iii) Reduce overlapping of licensing requirements; (iv) reduce potential discretionary behaviors | A. mapping and developing business regulatory processes in 5 BEE MDAs | Ekiti State Ministry of Finance shall work with the selected BEE MDAs to develop a business regulatory processes inclusive of fee structures in the State. | Ministry of Finance and Economic Development | Ekiti State Development and Investment Promotion Agency, Ministry of Housing, Ekiti State Signage and Advertising Agency, and Bureua of Lands, Ministry of Industry, Trade and Investment. | N500,000.00 | 2023-01-01 | 2023-06-30 | Done Impact - it has enhanced the efficiency of the process and increased the revenue of the State. it has reduced extortion and overbilling | a. 6 ministries, departments, and agencies of the Ekiti State government were identified as business enabling environment MDAs - Ministry of Trade and Investment, Ministry of Infrastructure and Public Utilities, Ministry of Physical Planning and Urban Development, Ekiti State Signage and Advertisement Agency, Ekiti State Inland Revenue Services and the Bureau of Land Services. b. The Ministry of Finance worked with the 6 identified MDAs to develop business regulatory processes, containing the processes, fees, services, and delivery timelines. c. These business regulatory processes are published on the state government's official website, the relevant MDA websites, and EKDIPA's website. | Not Applicable
|  |  | A.1. publication of the regulatory processes to include fees, services, delivery timelines in 5 Business Enabling Environment (BBE) MDAs on the State official website | Publish the business regulatory processes put in place on the official website of the State so that old and new business owners can access it easily | Ministry of Finance and Economic Development | Ekiti State Development and Investment Promotion Agency, Ministry of Housing, Ekiti State Signage and Advertising Agency, and Bureua of Lands, Ministry of Industry, Trade and Investment. | N450,000.00 | 2023-01-01 | 2023-06-30 | Done Impact - this action step will ensure easy access to the regulatory procedures by business owners. It also enhances the transparency of the procedures. It will further result in quick and efficient service delivery | Adoption of digital platforms and technologies to streamline regulatory processes enable online submissions, tracking of applications, and real-time updates on status. | Not Applicable
|  |  | A.2. develop State Grievance Redress Mechanism with legal backing | EKDIPA will develop guidelines for Grievance Redress Mechanism (GRM) and ensure it has the required legal support | Ekiti State Development and Investment Promotion Agency | Ministry of Industry, Trade and Investment, and Ministry of Justice | Not Applicable | 2023-01-01 | 2023-06-30 | Done Impact - it will provide legal backing for the establishment of GRM for the BEEs MDAs quick and affordable access to the resolution of disputes. Reduces harassment of business owners by government officials | a. EKDIPA developed the guidelines for the Grievance Redress Mechanism (GRM). b. An Executive Order was signed in 2023 to give the required legal backing to the GRM. | (i) Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion. (ii) organise stakeholder engagement sessions to sensitize the business community in Ekiti State on GRM
|  |  | A.3 development of Service level agreements in the 5 BEE MDAs | The Office of the Head of Service shall coordinate the BEE MDAs to reach a level of agreement on service areas for each MDA to remove overlapping roles | Office of the Head of Service | Ekiti State Development and Investment Promotion Agency, Ministry of Housing, Ekiti State Signage and Advertising Agency, and Bureua of Lands, Ministry of Industry, Trade and Investment. | Not Applicable | 2023-01-01 | 2023-06-30 | Not Started Impact - it will increase the commitment of the BEE MDAs to service delivery without delay. Clear procedures for accessing public services ensure that eligible individuals and organizations receive timely and equitable services without undue barriers or delays | Challenge - lack of technical resources to develop and publish the service level agreements. | i. Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion. (ii) create awareness on the implementation of the SLAs
|  |  | A.4. issuance of State Executive Order to direct 5 BEE MDAs to publish on State offcial website(s) their fees, procedures, SLAs, GRM, and manadatory advance communication rule | An Executive order directing the BEE MDAs to publish their fees, procedures, SLAs, GRM and mandatory advance communication rule on the State official website | Ekiti State Development and Investment Promotion Agency | Office of the Head of Service, Secretary to the State Government | Not Applicable | 2023-01-01 | 2023-06-30 | Done Impact - it makes it mandatory for the MDAs to carry out their mandate in the SLAs, GRM, and Communication Strategy. | a. The Executive Order 01, 2023 on the Promotion of Transparency and Efficiency in the Business Environment in Ekiti State was issued in 2023. b. It has provided an executive mandate for the MDAs on the clear procedures for accessing public services and ensuring that eligible individuals and organizations receive timely and equitable services without undue barriers or delays. | Not Applicable
|  |  | A.5 online publication of the report on monthly basis the operation and implementation of the GRM and SLAs in the 5 BEE MDAs | Publish monthly reports on GRM and SLA compliance on the State website. | Ekiti State Development and Investment Promotion Agency | office of the Head of Service | Not Applicable | 2023-01-31 | 2023-12-31 | Not Started Impact - there will be easy access to the information on the operation and implementation of the GRM and SLAs in the BEEs MDAs it would promote clarity and easy access to the report on the activities of the BEEs MDAs. | Challenge: lack of technical resources to implement. | Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
5 | Domestic and external trade competitiveness | To reduce and regulate multiple formal and informal checkpoints on inter-state movement of goods | A. establishment and online publication of schedule of trade related fees and levies on inter-state movement of goods | Provide comprehensive information on schedule trade related fees and levies on inter-State movement of goods | Ministry of Industry, Trade and Investment | Bureau of Information and Communication Technology, and Ekiti State Internal Revenue Service | Not Applicable | 2023-01-01 | 2023-02-28 | Done Impact - reduce extortion and provide easy access to information on the schedule of trade related fees and levies on inter-state movement of goods. These reforms are crucial for promoting inclusive economic growth and enhancing the overall efficiency of supply chains across states. | Publication of the schedule of trade-related fees and levies. it is easily accessible to stakeholders, including businesses, logistics providers, and the public. The link to the schedule of fees is below - https://ekdipa.com.ng/ekdipa-api/sites/default/files/2022-11/shedule%20of%20traderelated%20fees%20and%20levies.pdf | Not Applicable
|  |  | A.1. sensitization on the schedule of trade related fees and levies on inter-state movement of goods | Conduct advocacy meetings with groups and unions, emabrk on distribution of leaflets and lfiers to sensitize the operators | Ministry of Industry, Trade and Investment | Ministry of Information, Ekiti State Internal Revenue Service | N5,000,000.00 | 2023-01-01 | 2023-03-31 | Ongoing Impact - the sensitization will help to create more awareness about the schedule of all trade related fees and levies on inter-state movement of goods | Milestone - Design and implementation of a comprehensive strategy to educate stakeholders, including businesses, transporters, customs agents, and the public, about the newly established schedule of trade-related fees and levies. Challenge - The sensitization session did not hold in 2023 due to time constraints | Organise at least one sensitization programme with all relevant stakeholders.
|  |  | B. establishment of GRM for traders with SMS/hotline for reporting and redress | Establish an office and appoint a desk officer whose phone number shall be made available to the public to receive complaints | Ekiti State Development and Investment Promotion Agency | Ministry of Trade and Industry, Head of Service and Secretary to the State Government | N1,500,000.00 | 2023-01-01 | 2023-06-30 | Done Impact - GRM is expected to reduce conflict and provide a constructive outlet for resolving disputes and preventing escalation on trade related matters | Milestone - Feedback Mechanism on the issue relating to inter-state movement of Goods. A desk officer has been appointed to receive complaints on the hotline with a designated phone number. Challenge - Insufficient technical knowledge on GRM poses a potential challenge to the sustainability of this process. | convene an engagement session with the relevant stakeholders on GRM (ii) provide further training opportunities to the appointed desk officer on GRM. )iii) identify additional persons who can be trained as GRM desk officers to ensure sustainability.
|  |  | B.1 reporting on issues which are addressed by the GRM on monhly basis | Produce a monthly report of their activities to the Ministry for monitoring purpose | Ekiti State Development and Investment Promotion Agency | BEE MDAs | Not Applicable | 2023-06-30 | 2023-12-31 | Not Started Impact - The monthly report of the GRM will enhance transparency in the GRM; it will also aid the monitoring and evaluation of the effectiveness of the GRM System | Challenge - lack of technical resources to implement. | Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | C. establishment of State Committee on Export promotion (SCEP) | The Committee had been already been put in place | Ministry of Industry, Trade and Investment | Ministry of Agric and Food Security, Nigerian Export Promotion Council | N1,800,000.00 | 2023-01-01 | 2023-01-31 | Done Impact - The State Committee on Export Promotion shall enhance the promotion of exportation in Ekiti State | MIlestone - development of the Ekiti State Export Promotion Strategy | ensure that the Committee meets regularly to work towards the implementation of the guildelines and strategy on export
|  |  | C.1 allocation of an operational budget to the SCEP in the 2024 budget | Ministry of Trade shall include the SCEP in its 2024 budget estimate | Ministry of Industry, Trade and Investment | Ministry of Budget and Economic Planning, Ministry of Finance | N1,800,000.00 | 2023-01-01 | 2023-12-31 | Done Impact - the operational budget shall enable the SCEP to carry out its activities effectively | Milestone - the Committee has been able to kick start its operations without delay | Not Applicable
|  |  | D. develop Ekiti State export strategy and guidelines | A strategy leveraging the One State One product for Export national strategy should be developed | Ministry of Industry, Trade and Investment | Nigerian Export Promotion Council, Ministry of Agriculture and Food Security | Not Applicable | 2023-01-01 | 2023-03-31 | Done Impact - The Strategy will provide clear direction for the operation of the SCEP | The export strategy has contrbuted to growth of MSMEs in the State | Not Applicable
|  |  | D.1 online publication of Ekiti State Export Strategy and Guildelines | Ministry of Trade with BICT shall publish the State Export Strategy and Guildelines for easy accessibility | Ministry of Industry, Trade and Investment | Bureau of Information and Communication Technology | Not Applicable | 2023-04-01 | 2023-06-30 | Done Impact - The online publication of the Strategy and Guidelines on Export will enable all relevant stakeholders have access to the document. | The state government published the Strategy and Guidelines on (https://ekitistate.gov.ng/wp-content/uploads/saber/STATE%20EXPORT%20STRATEGY%20AND%20GUIDELINE.pdf) These reforms are crucial for promoting inclusive economic growth and enhancing the overall efficiency of supply chains across states. It further enhances the transparency of the activities of the SCEP | Not Applicable
|  |  | E. eliminate haulage fees and charges in year 2024 | Ministry of Trade and other BEE MDAs shall gradually work out the removal of haulage fees and charges by end of 2025 by obtaining the approval of the Governor | Ministry of Industry, Trade and Investment | Ekiti State Internal Revenue Services, Ministry of Finance and Economic Development | Not Applicable | 2023-12-01 | 2023-12-31 | Not Started Impact - Eliminating fees can simplify supply chain operations, improving overall efficiency. reforming to reduce and regulate multiple, formal, and informal checkpoints on inter-state movement of goods can unlock significant economic benefits, improve business competitiveness, reduce administrative burdens, and foster a more conducive environment for trade and investment. | Not Applicable | Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | F. increase the number of firms with export certificates from Nigerian Export Promotion Council (NEPC) attracted to Ekiti State | SCEP and Ministry of Trade shall make sensitization campaign to attract new Exporters with incentives put in place to help Export business in the State | Ministry of Industry, Trade and Investment | Nigerian Export Promotion Council, Ministry of Information | N500,000.00 | 2023-01-01 | 2024-01-01 | Ongoing Impact - An increase in number of firms with export certificates will ensure increase of exportation in the State; The action is to encourage more business owners to apply for export certificate. It would boost the IGR to grow the economy of the State | Challenge Lack of Knowledge: Many businesses are unaware of the benefits of export certification and the process involved. | (i) Write to NEPC to request the number of firms with export certificates in Ekiti State. (II) Create a list of all firms carrying out export business in Ekiti State, starting with the agriculture and manufacturing sectors. (iii) organise and hold a sensitization session with these firms on the need to obtain export certificates. (iv) create a supportive environment for firms seeking export certification in Ekiti State by curating a special programme within EKDIPA that caters to their export needs. (v) Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
6 | simplification of State and Local Business Tax Regimes | This reform is aimed at making it easy to understand and make payment for tax in Ekiti State | A. review the existing State revenue law to adopt presumptive turnover tax regime for small businesses | To review the Ekiti State Board of Internal Revenue Law | Ekiti State Internal Revenue Services | Ministry of Finance and Economic Development, Ministry of Justice and Ekiti State House of Assembly | Not Applicable | 2023-01-01 | 2023-06-30 | Not Started Impact - the review of the existing law is necessitated by the need to provide legal backing for the establishment of a presumptive turnover tax regime for small businesses in Ekiti State | Challenges: The action could not be achieved due to time constraints and non-availability of technical resources to achieve implementation. | Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | A.1 establish a presumptive turnover tax regime for small busniesses in Ekiti State | Achieve 100% growth in both number of taxpayers and value of taxes collected | Ekiti State Internal Revenue Services | Ministry of Industry, Trade and Investment, and Ministry of Local Government | Not Applicable | 2023-01-01 | 2023-06-30 | Not Achieved Impact - The clarity of the presumptive tax regime will lead to higher compliance rates as taxpayers are more likely to pay their taxes correctly and on time. | The action was not achieved due to lack of legal backing for presumptive turnover tax. | Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | B. subsume all business-related local government charges/fees/taxes into a consolidated demand notice | Generate harmonized Demand Notice | Ekiti State Internal Revenue Services | Ministry of Local Government, Ministry of Trade and Ministry of Infrastructure and Public Utilties | Not Applicable | 2023-01-01 | 2023-04-01 | Not Started Impact - elimination of multiple taxations Subsuming business-related local government charges/fees/taxes into a consolidated demand notice would enhance clarity and simplicity in the payment of taxes/fees and fees by the business owners in Ekiti State | Challenges: (i) Non-availability of technical resources to achieve completion. (ii) inability to meet with the chairmen of the local government owing to time constraints | (i)Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion. (ii) Stakeholders engagement with the Local Governments;
|  |  | B.1 raise consolidated demand notices for all business-related local government charges/fees/taxes | Print and serve consolidated Demand Notices | Ekiti State Internal Revenue Services | Ministry of Local Government, Ministry of Trade and Ministry of Infrastructure and Public Utilties | Not Applicable | 2023-03-31 | 2023-04-30 | Not Achieved- consolidated demand notice makes payment for taxes/fees/charges easy |  | Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | C. establish electronic platform for collection of taxes,levies and fees from businesses and generate automated e-receipt (QR code or unique payment ID) for all BEE MDAs | Develop Electronic Payment Solution | Ekiti State Internal Revenue Services | Ministry of Local Government, Ministry of Trade and Ministry of Infrastructure and Public Utilties | Not Applicable | 2023-01-01 | 2023-06-30 | Not Started Impact - this action step will enhance easy payment of taxes. Simplifying tax regulations and procedures reduces confusion and ambiguity, making it easier for individuals and businesses to understand their tax obligations. This clarity typically leads to higher compliance rates as taxpayers are more likely to pay their taxes correctly and on time. | Challenge - non availability of technical resources to achieve completion. | Recaptured in the 2024 Business Enabling Reform Action Plan (BERAP) to ensure completion.
|  |  | D. ensure electronic payment of all State-level and local government taxes, levies and fees from business (with adoption of at least 75% of State collection of taxes, levies and fees from businesses | Increase adoption of electronic Payment of taxes | Ekiti State Internal Revenue Services | Ministry of Local Government, Ministry of Trade and Ministry of Infrastructure and Public Utilties | Not Applicable | 2023-01-01 | 2023-04-01
7 | Quick determination of commercial disputes | This reform area will improve the State Judiciary and strengthen access to an efficient commercial justice system | A. establishment of State Judicial Committee by the Chief Judge of Ekiti State Judiciary | The Chief Judge of Ekiti State Judiciary shall obtain the approval of the Governor for the establishment of Judicial Committee | Ekiti State Judiciary | Ministry of Justice, Office of the Secretary to the State Government, | Not Applicable | 2023-01-01 | 2023-06-30 | Done Impact - The Judicial Committee of the Small Claims Courts oversees the activities of the Courts and ensures it operates in line with the Practice Directions. This efficiency will boost confidence in the legal system and encourages businesses to invest and operate with certainty. | a. The Honourable Chief Judge estbalished the Judicial Committee of Small Claims Court. b. The State Judicial Committee supported the development of the Small Claims Courts Practice Directions. c. The Committee is responsible for monitoring the performance of the small claims courts, especially the Monthly Performance Report, ensuring that matters are concluded within 60 days. The link to the letter establishing the Judicial Committee on Small Claims Court is below - https://ekitijudiciary.ek.gov.ng/uploads/Small%20Claims%20Committee.pdf | a. The Committee will monitor the small claims courts activities, especially its adherence to the Practice Directions. b. The Committee will hold regular meetings with the Magistrates in charge of the Small Claims Courts.
|  |  | B. establishment and operation of small claims courts (tried at least one case each) | The Judicial Committee shall appoint some judges to precide over the small claims courts in the State | Ekiti State Judiciary | Ministry of Justice | Not Applicable | 2023-01-01 | 2023-01-31 | Done Impact - The establishment of Small Claims Court in Ekiti State will ensure speedy, easy and affordable access to justice for MSMEs doing business in the State | The Honourable Chief Judge of Ekiti State designated 4 additional magistrate courts as Small Claims Courts in Ekiti. The additional courts were designated in Ado, Ikere and Ikole Magistrate Divisions. | (i) create awareness on the establishment of the Small Claim Courts (ii) training of court officials to ensure they have the necessary expertise to adjudicate cases efficiently in the small claim courts.
|  |  | B.1 Development of the State Judiciary website | to ensure transparency, the State Judiciary shall establish a functional website | Ekiti State Judiciary | Ministry of Justice | N10,000,000.00 | 2023-01-01 | 2023-06-30 | Done Impact - the website will enhace the transparency of the judicial processes in Ekiti State including that of the Small Claim court | a. the inclusion of comprehensive and up-to-date information on the website. This includes details about the judiciary's structure, organization, judges, court locations, contact information, and operating hours. b. Information such as the practice directions and handbook of the Small Claims Court are published on the Judiciary's website. c. The Monthly Performance of the Small Claims Court including details about cases to ensure that these matters are disposed of within 60 days are published on the Judiciary's website. The link of Ekiti State Judiciary website - https://ekitijudiciary.ek.gov.ng/ | a. regular maintenance and updating of the website b. publication of small claims courts monthly performance reports.
|  |  | B.2 publication on State Judiciary website the practice Directions of the small claims courts | to ensure transparency, the State Judiciary shall establish a functional website | Ekiti State Judiciary | Ministry of Justice, BICT | Not Applicable | 2023-01-01 | 2023-06-30 | Done Impact - Publishing the practice directions on the website ensures that litigants, lawyers, and stakeholders have easy access to the procedural guidelines and rules governing small claims court proceedings. This promotes clarity and understanding of the court's processes | Ekiti State Judiciary's Small Claims Courts Practice Directions was developed and published on the Judiciary's website. The link to the practice direction as published on the website - https://ekitijudiciary.ek.gov.ng/uploads/PDF2%20gazette%20magistrate%202023-1.pdf | not Applicable
|  |  | B.3. write monthly report for small claims courts from inception of the courts to December 2023 | The Judiciary shall provide a monthly report on the activities of the small claims court on a monthly basis | Ekiti State Judiciary | Ministry of Justice | Not Applicable | 2023-01-01 | 2023-12-31 | Done Impact - The submission of the monthly report promotes accountability by ensuring that litigants and the public can track the courts' performance to confirm adherence to the 60-day timeline for the disposition of small claims. | a. The court has been manually compiling the report of the small claims courts since its inception in 2020. b. The state judiciary is adopting a digitized process for the compilation of the monthly performance report of small claims court. c. The court began the use of the new digitized template in 2024. | a. The Magistrates will compile and submit the monthly reports of cases handled by their courts. b. The Judicial Committee on Small Claims Courts will oversee and track the timely submission of the monthly performance reports.
|  |  | B.4. publication on the State Judiciary website reports for small claims courts on monthly basis | The Judiciary shall provide a monthly report on the activities of the small claims court on a monthly basis | Ekiti State Judiciary | Ministry of Justice | Not Applicable | 2023-01-01 | 2023-06-30 | Done Impact - The publication of the monthly report promotes accountability by ensuring that litigants and the public can track the courts' performance to confirm adherence to the 60-day timeline for the disposition of small claims. | a. The court has been manually compiling the report of the small claims courts since its inception in 2020. b. The state judiciary is adopting a digitized process to compile the monthly performance report of small claims court. c. The court began the use of the new digitized template in 2024. d. increase in public confidence in the activities of the courts. The link to the report of the small claim court - https://ekitijudiciary.ek.gov.ng/monthly-reports-on-small-claims-court/ | This action step is recaptured in the 2024 State Business Enabling Reform Action Plan (BERAP) for continuous execution.
|  |  | C. submit dispostion time report to include the % of cases dispose within 60 days | The Judiciary shall provide a monthly report on the activities of the small claims court on a monthly basis and ensuee at least 80% performance achievement | Ekiti State Judiciary | Ministry of Justice | Not Applicable | 2023-01-01 | 2023-06-30 | Done Impact - The submission of the monthly report promotes accountability by ensuring that litigants and the public can track the courts' performance to confirm adherence to the 60-day timeline for the disposition of small claims. | a. The court has been manually compiling the report of the small claims courts since its inception in 2020. b. The state judiciary is adopting a digitized process for the compilation of the monthly performance report of small claims court. c. The court began the use of the new digitized template in 2024. | This action step is recaptured in the 2024 State Business Enabling Reform Action Plan (BERAP) for continuous execution.
|  |  | D. submit execution time report to include the % of judgement executed within 30 days | The Judiciary shall provide a monthly report on the activities of the small claims court on a monthly basis and ensuee at least 80% performance achievement | Ekiti State Judiciary | Ministry of Justice | Not Applicable | 2023-01-01 | 2023-06-30 | Done Impact - The submission of the monthly report promotes accountability by ensuring that litigants and the public can track the courts' performance to confirm adherence to the 60-day timeline for the disposition of small claims. | a. The court has been manually compiling the report of the small claims courts since its inception in 2020. b. The state judiciary is adopting a digitized process for the compilation of the monthly performance report of small claims court. c. The court began the use of the new digitized template in 2024. | This action step is recaptured in the 2024 State Business Enabling Reform Action Plan (BERAP) for continuous execution.